## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | fall2015/spring2016 | s16b_Picshare_RA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team01\team01b\Development\RCP | N/A
2 | fall2015/spring2016 | s16b_Picshare_AA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team02\team02b\new\Final Deliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.61 | 53… | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
|  |  |  | Communication Module | 220 | 0.55 | 0.73 | 0.4 | 543.41 | 0.1
|  |  |  | Money Transaction Module | 880 | 0.6 | 2.94 | 1.76 | 499.44 | 0.3
|  |  |  | Queue Management | 440 | 0.7 | 1.47 | 1.02 | 431.33 | 0.1
|  |  |  | Website | 840 | 0.42 | 2.8 | 1.18 | 713.31 | 0.2
4 | Fall 11 |  | ~\577 projects\fall2011\projects\team04\team04a\FinalDelivery | Attendance Data Input System | 800 | 0.74
|  |  |  | Performance Report (grade/attendance) | 800 | 1.1
|  |  |  | Grade data import system | 400 | 0.57
|  |  |  | Notification System | 400 | 0.63
|  |  |  | Resource Management | 500 | 0.65
|  |  |  | System Management | 600 | 0.74
|  |  |  | Data request processing system | 600 | 1.12
7 | Fall 11 |  | ~\577 projects\fall2011\projects\team07\Foundations | Data Migration | 231 | 0.88
|  |  |  | Password Recovery | 200 | 0.75
9 | Fall 11 |  | ~\577 projects\fall2011\projects\team09\team09a\FD | N/A
10 | Fall 11 |  | ~\577 projects\fall2011\projects\team10\finaldeliverables | Authentication Module | 619 | 0.81
|  |  |  | Recruitment Module | 1750 | 0.92
|  |  |  | Job Listing Module | 1241 | 0.92
5 | Fall 11/Spring 12 |  | ~\577 projects\spring2012\projects\team05\FD | N/A
11 | Fall 11/Spring 12 |  | ~\577 projects\spring2012\projects\team11\FD | N/A
12 | Fall 11/Spring 12 |  | ~\577 projects\spring2012\projects\team12b\Development | Student Course Preference Module | 483 | 0.81
|  |  |  | Interation with Scheduling COTS (FET) | 175 | 0.91
|  |  |  | Database | 14 | 0.88
|  |  |  | Teacher Course Allocation Module | 6 | 0.71
|  |  |  | Head Scheduler Data entry module | 823 | 0.8
|  |  |  | Student Course Allocation Module | 498 | 0.81
|  |  |  | Student Progress Trading Module | 18 | 0.78
|  |  |  | Family accountability integration module | 233 | 1.13
14 | Fall 11/Spring 12 |  | ~\577 projects\spring2012\projects\team14\Development\IOC2 | N/A
13 |  |  |  | N/A
1 | Fall 11 |  | ~\577 projects\fall2011\projects\team01\team01a\FD | N/A
3 | Fall 11 |  | ~\577 projects\fall2011\projects\team03\team03a\FD | N/A
6 | Fall 11 |  | ~\577 projects\fall2011\projects\team06\team06a\FD | N/A
8 | Fall 11 |  | ~\577 projects\fall2011\projects\team08\team08a\FD | Error Checking | 1000 | 1.22
|  |  |  | View Reports | 1000 | 0.85
|  |  |  | Logout | 150 | 0.74
|  |  |  | Export File | 1000 | 0.27
|  |  |  | Login | 150 | 0.92

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab