## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | fall2015/spring2016 | s16b_Picshare_RA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team01\team01b\Development\RCP | N/A
2 | fall2015/spring2016 | s16b_Picshare_AA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team02\team02b\new\Final Deliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.61 | 53… | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
|  |  |  | Communication Module | 220 | 0.55 | 0.73 | 0.4 | 543.41 | 0.1
|  |  |  | Money Transaction Module | 880 | 0.6 | 2.94 | 1.76 | 499.44 | 0.3
|  |  |  | Queue Management | 440 | 0.7 | 1.47 | 1.02 | 431.33 | 0.1
|  |  |  | Website | 840 | 0.42 | 2.8 | 1.18 | 713.31 | 0.2

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab