## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | fall2015/spring2016 | s16b_Picshare_RA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team01\team01b\Development\RCP | N/A
2 | fall2015/spring2016 | s16b_Picshare_AA | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team02\team02b\new\Final Deliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.61 | 53… | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
|  |  |  | Communication Module | 220 | 0.55 | 0.73 | 0.4 | 543.41 | 0.1
|  |  |  | Money Transaction Module | 880 | 0.6 | 2.94 | 1.76 | 499.44 | 0.3
|  |  |  | Queue Management | 440 | 0.7 | 1.47 | 1.02 | 431.33 | 0.1
|  |  |  | Website | 840 | 0.42 | 2.8 | 1.18 | 713.31 | 0.2
1 | fall2013/spring2014 |  | ~\577 projects\spring14\projects\team01\Development | User profile and CV module | 1500 | 0.73
|  |  |  | Search Module | 2000 | 1.14
|  |  |  | Collaboration List Module | 500 | 0.48
|  |  |  | Pumbed Pulling Module | 1200 | 1.56
|  |  |  | Discussion Board and Messaging Module | 200 | 0.57
5 |  |  | ~\577 projects\fall2013\projects\team05a\team05\Foundations | Payment | 100 | 0.75 | 0.3 | 0.2 | 439.3 | 0 | 3.8 | 4.5 | 465.9 | 0.8 | 4.8 | 4.9 | 372.8 | 1 | 6 | 5.2 | 298.2 | 1.1
|  |  |  | rank and review | 100 | 0.63 | 0.3 | 0.2 | 525.3 | 0
|  |  |  | order manage | 315 | 0.68 | 1 | 0.7 | 483.3 | 0.1
|  |  |  | Searching | 420 | 0.78 | 1.3 | 1 | 420.4 | 0.2
|  |  |  | user manage | 420 | 0.99 | 1.3 | 1.3 | 331.9 | 0.3
|  |  |  | Product manage | 420 | 1.12 | 1.3 | 1.4 | 294.2 | 0.3
6 | fall2013/Spring 2014 |  | ~\577 projects\fall2013\projects\team06a\team06\Development |  | 630 | 0.42 | 2.1 | 0.9 | 730.4 | 0.1 | 6 | 6.4 | 823.3 | 0.9 | 7.5 | 6.9 | 658.7 | 1.1 | 9.4 | 7.4 | 526.9 | 1.3
|  |  |  | Const Procs | 840 | 0.35 | 2.7 | 1 | 880.9 | 0.1
|  |  |  | StudyPlan Cons | 550 | 0.58 | 1.8 | 1 | 524.6 | 0.2
|  |  |  | Deg Req Cons | 525 | 0.47 | 1.7 | 0.8 | 655.1 | 0.1
|  |  |  | View Control | 1050 | 0.29 | 3.4 | 1 | 1049.9 | 0.1
|  |  |  | Authentication | 330 | 0.35 | 1.1 | 0.4 | 880.9 | 0.1
|  |  |  | Solver | 1040 | 0.73 | 3.4 | 2.5 | 416.4 | 0.4
9 | fall 2013 |  | ~577projects\fall2013\projects\team09\team09a\Valuation | N/A
14 | fall 2013 |  | ~577projects\fall2013\projects\team14\team14b\team14b\Development | Survey Import | 495 | 0.41 | 1.69 | 0.69 | 722.49 | 0.1 | 6.25 | 6.55 | 852.27 | 1 | 7.82 | 7.03 | 681.81 | 1.1 | 9.77 | 7.54 | 545.45 | 1.3
|  |  |  | Survey Configuration | 2300 | 0.37 | 7.85 | 2.89 | 794.74 | 0.4
|  |  |  | Survey Database | 525 | 0.45 | 1.79 | 0.81 | 644.38 | 0.1
|  |  |  | Survey Completion | 1680 | 0.52 | 5.74 | 2.97 | 566.28 | 0.4
|  |  |  | Survey Export | 330 | 0.41 | 1.13 | 0.46 | 722.49 | 0.1
3 | fall2013/spring2014 |  | ~\577 projects\fall2013\projects\team03a\Development | Search Module | 263 | 0.52 | 0.8 | 0.42 | 633 | 0.1 | 3.56 | 5.48 | 391.28 | 0.6 | 4.45 | 5.88 | 313.02 | 0.8 | 5.56 | 6.31 | 250.42 | 0.9
|  |  |  | Lesson Module | 360 | 0.89 | 1.09 | 0.97 | 370 | 0.2
|  |  |  | Inventory Module | 330 | 1.35 | 1 | 1.35 | 244 | 0.2
|  |  |  | Survey Module | 385 | 1.32 | 1.17 | 1.53 | 250 | 0.3
|  |  |  | Student Module | 55 | 1.09 | 0.17 | 0.18 | 303 | 0
4 | fall 2013 |  | ~\577 projects\fall2013\projects\team04a\team04\Development | Tumblr Share Module | 150
|  |  |  | Facebook Share Module | 350
|  |  |  | Twitter Share Module | 180
|  |  |  | Friendship Module | 400
|  |  |  | Account Module | 200
|  |  |  | Featured video lists | 408 |  |  |  |  | 0.3
|  |  |  | Video Tagging | 354 |  |  |  |  | 0.3
6 | fall2013/spring14 |  | ~\577 projects\fall2013\projects\team06a\team06\Development | Video Rendering | 1050 | 0.42 | 3.2 | 1.33 | 789.96 | 0.3 | 2.53 | 4.89 | 790.7 | 0.5 | 3.17 | 5.24 | 632.56 | 0.6 | 3.96 | 5.61 | 506.05 | 0.7
|  |  |  | Linking Tool | 954 | 0.63 | 2.91 | 1.84 | 518.79 | 0.4
12 | fall 2013 |  | ~577projects\fall2013\projects\team12\team12a\team12a\FD | N/A | [6 empty] | 54.11 | 12.68 | 333.37 | 4.3 | 67.64 | 13.6 | 266.7 | 5 | 84.55 | 14.57 | 213.36 | 5.8
16 | fall 2013 |  | ~577projects\fall2013\projects\team16\team16a\Archive\FinalDeliverables\TRR | supervisor and Volunteer Management System | 1428 | 1.17 | 4.67 | 5.46 | 261.57 | 0.7 | 9.91 | 7.58 | 327.68 | 1.3 | 12.39 | 8.13 | 262.14 | 1.5 | 15.48 | 8.73 | 209.71 | 1.8
|  |  |  | Victim state monitoring System | 406 | 1.37 | 1.33 | 1.82 | 223.57 | 0.2
|  |  |  | Transport Coordinator Management System | 203 | 1.2 | 0.66 | 0.79 | 255.69 | 0.1
|  |  |  | Communication System | 304 | 1.17 | 0.99 | 1.16 | 261.57 | 0.1
|  |  |  | Security System | 101 | 1.2 | 0.33 | 0.4 | 255.69 | 0
|  |  |  | Mobile Victim Data Entry and retrieval System | 805 | 1.05 | 2.63 | 2.76 | 291.68 | 0.3
2 | Fall 2013 |  | ~\577 projects\fall2013\projects\team02\team02b\Development | Server | 3200 | 0.24 | 10.63 | 2.52 | 12 | 0.4
|  |  |  | UI | 3000 | 0.29 | 9.96 | 2.89 | 10 | 0.5
7 | Fall 2013 |  | ~\577 projects\fall2013\projects\team07\team07b\IOC #1& TS Set | Ranking System | 220 | 0.63 | 0.72 | 0.45 | 485 | 0.1 | 6.88 | 6.72 | 551.77 | 1 | 8.6 | 7.21 | 441.41 | 1.2 | 10.75 | 7.73 | 353.3 | 1.4
|  |  |  | Search Engine | 2750 | 0.63 | 8.98 | 5.63 | 488 | 0.8
|  |  |  | Recommendation System | 825 | 0.94 | 2.69 | 2.52 | 327 | 0.3
8 | Fall 2013 |  | ~\577 projects\fall2013\projects\team08\team08b\Final Deliverables | Profile Management | 350 | 1.39 | 1.15 | 1.6 | 218 |  | 11.91 | 8.08 | 251.87 | 1.5 | 14.89 | 8.67 | 201.5 | 1.7 | 18.61 | 9.31 | 161.2 | 2
|  |  |  | Donation Management | 1100 | 1.94 | 3.62 | 7.04 | 156
|  |  |  | Goal Creation And Tracking | 500 | 1.39 | 1.64 | 2.29 | 218
|  |  |  | Reward Management | 350 | 1.26 | 1.15 | 1.45 | 241
|  |  |  | marketing Management | 700 | 1.09 | 2.3 | 2.52 | 277
10 | Fall 2013 |  | ~\577 projects\fall2013\projects\team10\team10b\FD\AsbuiltPackage\AsbuiltSet | Data Entity(Database) | 69 | 0.17 | 0.24 | 0.04 | 166 | 0 | 9.17 | 7.38 | 847.76 | 1.2 | 11.47 | 7.92 | 678.21 | 1.4 | 14.33 | 8.5 | 542.56 | 1.7
|  |  |  | Data Access(Model) | 861 | 0.15 | 3.02 | 0.45 | 189 | 0.1
|  |  |  | Data Processing(Controller) | 630 | 0.19 | 2.21 | 0.41 | 153 | 0.1
|  |  |  | Scheduling Solver(Controller) | 1725 | 0.77 | 6.05 | 4.68 | 368.58 | 0.6
|  |  |  | Student Side GUI(View) | 2136 | 0.37 | 7.5 | 2.8 | 763.74 | 0.4
|  |  |  | Administrative Side Gui(View) | 2355 | 0.37 | 8.27 | 3.08 | 763.74 | 0.4
11 | Fall 2013 |  | ~\577 projects\fall2013\projects\team11\team11a\FD | Slot posting | 525 | 0.7 | 1.71 | 1.2 | 436.25 | 0.2 | 7.19 | 6.8 | 569.52 | 1.1 | 8.99 | 7.3 | 455.62 | 1.2 | 11.23 | 7.82 | 364.49 | 1.4
|  |  |  | Email alert module | 550 | 0.64 | 1.8 | 1.15 | 479.88 | 0.2
|  |  |  | Profile module | 420 | 0.7 | 1.37 | 0.96 | 436.25 | 0.1
|  |  |  | Reservation module | 840 | 0.7 | 2.74 | 1.93 | 436.25 | 0.3
|  |  |  | Payment module | 330 | 0.7 | 1.08 | 0.76 | 436.25 | 0.1
|  |  |  | Monitor module | 550 | 0.59 | 1.8 | 1.05 | 521.61 | 0.1
|  |  |  | Search module | 880 | 0.67 | 2.87 | 1.94 | 453.8 | 0.3
13 | Fall 2013 |  | ~\577 projects\fall2013\projects\team13\team13b\team13b\FD | 2D Visualisation | 308 | 1.08 | 0.96 | 1.04 | 294 | 0.2 | 11.46 | 5.23 | 305.94 | 2.2 | 14.33 | 5.6 | 244.75 | 2.6 | 17.91 | 6 | 195.8 | 3
|  |  |  | 3D Visualisation | 1188 | 1.45 | 3.72 | 5.4 | 220 | 1
|  |  |  | Authentication | 420 | 0.94 | 1.32 | 1.24 | 338 | 0.2
|  |  |  | Data Entry | 315 | 0.94 | 0.99 | 0.93 | 338 | 0.2
|  |  |  | Sphere Editing | 1276 | 1.43 | 4 | 5.71 | 223 | 1
15 | Fall 2013 |  | ~\577 projects\fall2013\projects\team13\team13b\team13b\FD | Check in | 1000 | 0.97 | 3.37 | 3.27 | 305.76 | 0.4 | 8.52 | 7.27 | 422.36 | 1.2 | 10.65 | 7.81 | 337.89 | 1.4 | 13.32 | 8.39 | 270.31 | 1.6
|  |  |  | Authentication | 400 | 0.91 | 1.35 | 1.23 | 325.22 | 0.3
|  |  |  | Student Management | 500 | 1.23 | 1.69 | 2.07 | 241.39 | 0.2
|  |  |  | Document Management | 400 | 0.66 | 1.35 | 0.89 | 446.95 | 0.1
|  |  |  | Site Management | 700 | 0.66 | 2.36 | 1.57 | 446.95 | 0.2
|  |  |  | Schedule Component | 600 | 0.8 | 2.02 | 1.62 | 370.07 | 0.2

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab