## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | Effort (PM) | Effort (PH) | Staff | Other | Project | Method | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | fall2015/spring2016 | s16b_Picshare_RA | [6 empty] | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team01\team01b\Development\RCP | N/A
2 | fall2015/spring2016 | s16b_Picshare_AA | [6 empty] | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team02\team02b\new\Final Deliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.61 | 53… | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
[10 empty] | Communication Module | 220 | 0.55 | 0.73 | 0.4 | 543.41 | 0.1
[10 empty] | Money Transaction Module | 880 | 0.6 | 2.94 | 1.76 | 499.44 | 0.3
[10 empty] | Queue Management | 440 | 0.7 | 1.47 | 1.02 | 431.33 | 0.1
[10 empty] | Website | 840 | 0.42 | 2.8 | 1.18 | 713.31 | 0.2
3 | fall2012/wpring2013 |  | 0.48 | 73 | 6 |  | Web_based_product_configurator_and_data_service_system |  | ~\577 projects\spring2013\team03b\team03\Development | N/A
1 | fall2012 |  | 7.05 | 1099.8 | 5 |  | Pediatric_Trauma_Society_Research_Investigator_Databank _PTS_RID |  | ~\577 projects\spring2013\team01b\team01\Development | User Profile and CV Module | 1500 | 0.73
[10 empty] | Search Module | 2000 | 1.14
[10 empty] | Collaboration List Module | 500 | 0.48
[10 empty] | Pubmed Pulling Module | 1200 | 1.56
[10 empty] | Discussion Board and Messaging Module | 200 | 0.57
5 | fall2012/spring2013 |  | 4.8 | 748.8 |  |  | FlowerSeeker |  | ~\577 projects\spring2013\team05b\team05\Development | Payyment | 100 | 0.75 | 0.3 | 0.2 | 439.3 | 0 | 3.8 | 4.5 | 465.9 | 0.8 | 4.8 | 4.9 | 372.8 | 1 | 6 | 5.2 | 298.2 | 1.1
[10 empty] | rank and review | 100 | 0.63 | 0.3 | 0.2 | 525.3 | 0
[10 empty] | order manage | 315 | 0.68 | 1 | 0.7 | 483.3 | 0.1
[10 empty] | searching | 420 | 0.78 | 1.3 | 1 | 420.4 | 0.2
[10 empty] | user manage | 420 | 0.99 | 1.3 | 1.3 | 331.9 | 0.3
[10 empty] | product manage | 420 | 1.12 | 1.3 | 1.4 | 294.2 | 0.3
6 | fall2012/spring2013 |  | 7.5 | 1170 |  |  | Student_Scheduling_System |  | ~\577 projects\spring2013\team06b\team06\Development | Database | 630 | 0.42 | 2.1 | 0.9 | 730.4 | 0.1 | 6 | 6.4 | 823.3 | 0.9 | 7.5 | 6.9 | 658.7 | 1.1 | 9.4 | 7.4 | 526.9 | 1.3
[10 empty] | Const Procs | 840 | 0.35 | 2.7 | 1 | 880.9 | 0.1
[10 empty] | StudyPlan Cons | 550 | 0.58 | 1.8 | 1 | 524.6 | 0.2
[10 empty] | Deg Req Cons | 525 | 0.47 | 1.7 | 0.8 | 655.1 | 0.1
[10 empty] | View Control | 1050 | 0.29 | 3.4 | 1 | 1049.9 | 0.1
[10 empty] | Authentication | 330 | 0.35 | 1.1 | 0.4 | 880.9 | 0.1
[10 empty] | Solver | 1040 | 0.73 | 3.4 | 2.5 | 416.4 | 0.4
9 | fall2012/spring2013 |  | 1 | 100 | 6&4 |  | United_Direct_Marketing |  | ~\577 projects\spring2013\team09b\team09\Development | N/A
2 | fall2012 |  | NA | NA | NA |  | Mission_Science_Information_and_Data_Management_System_2.0 |  | ~\577 projects\fall2012\team02a\team02\ARB\TRR | N/A
4 | fall2012 |  | NA | 137 | 6 |  | Art_Crafts_Website | Application Point | ~\577 projects\fall2012\team04a\team04\ARB\DCR | N/A
7 | fall2012 |  | NA | NA | 6 | 920 | Web_Media_Modernization_2012 |  | ~\577 projects\fall2012\team07a\Development | N/A
8 | fall2012 |  | 2.21 | 336 | 6 |  | Improvementon_on_VITA_website |  | ~\577 projects\fall2012\team08a\Development | N/A
10 | fall2012 |  | 3.2 | 499.2 |  |  | XL_2 |  | ~\577 projects\fall2012\team10a\Development | Input Model | 1632 | 0.42 | 4.9 | 2.1 | 788.6 | 0.3 | 2.6 | 6.4 | 798.2 | 0.4 | 3.2 | 6.8 | 638.6 | 0.5 | 4 | 7.3 | 510.9 | 0.5
[10 empty] | Budget report | 100 | 0.58 | 0.3 | 0.2 | 575.7 | 0
[10 empty] | Cash Flow rep | 204 | 0.98 | 0.6 | 0.6 | 338.7 | 0.1
[10 empty] | Excel populate | 100 | 1.13 | 0.3 | 0.3 | 291.8 | 0.1

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab