## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | Effort (PM) | Effort (PH) | Staff | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | fall2015/spring2016 | s16b_Picshare_RA |  |  |  | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team01\team01b\Development\RCP | N/A
2 | fall2015/spring2016 | s16b_Picshare_AA |  |  |  | C:\Users\Kan Qi\Google Drive\ResearchSpace\Repositories\577 projects\fall2015\projects\team02\team02b\new\Final Deliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.61 | 53… | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
[7 empty] | Communication Module | 220 | 0.55 | 0.73 | 0.4 | 543.41 | 0.1
[7 empty] | Money Transaction Module | 880 | 0.6 | 2.94 | 1.76 | 499.44 | 0.3
[7 empty] | Queue Management | 440 | 0.7 | 1.47 | 1.02 | 431.33 | 0.1
[7 empty] | Website | 840 | 0.42 | 2.8 | 1.18 | 713.31 | 0.2
1 | fall2016 | f16a_frenzy | 7.13 | 1112.28 |  | ~577projects\fall2016\projects\f16team01\FD\As Built Package | Similar .. | 400 | 0.51 | 1.28 | 0.66 | 607 | 0.1 | 5.7 | 6.33 | 569.11 | 0.9 | 7.13 | 6.79 | 455.28 | 1.1 | 8.91 | 7.28 | 364.23 | 1.2
[7 empty] | Lower P.. | 367 | 0.89 | 1.18 | 1.05 | 350 | 0.2
[7 empty] | Same Be.. | 567 | 0.68 | 1.82 | 1.24 | 455 | 0.2
[7 empty] | shop widget | 1068 | 0.77 | 3.43 | 2.65 | 403 | 0.4
[7 empty] | Clothing Tag | 844 | 0.57 | 2.71 | 1.53 | 550 | 0.2
2 | fall2016 | f16a_vyma | 7.9 | 1232.4 |  | ~577projects\fall2016\projects\f16team02\FD | Registration | 900 | 0.78 | 2.9 | 2.3 | 394.6 | 0.3 | 6.3 | 6.5 | 595.4 | 1 | 7.9 | 7 | 476.3 | 1.1 | 9.8 | 7.5 | 381.1 | 1.3
[7 empty] | Payment System | 750 | 0.87 | 2.4 | 2.1 | 353.4 | 0.3
[7 empty] | Migration | 1200 | 0.53 | 3.9 | 2.1 | 575.1 | 0.3
[7 empty] | Announcements | 550 | 0.55 | 1.8 | 1 | 556.5 | 0.1
[7 empty] | Event Calander | 350 | 0.35 | 1.1 | 0.4 | 889.7 | 0.1
3 | fall2016 | f16a_GoGrrrlsApp | 1960 |  | 7 | ~577projects\fall2016\projects\f16team03\Project_docs\FD (Final Deliverables)\As Built Package | N/A
4 | fall2016 | f16a_ImageProcessing_Platform | 8.3 | 1294.8 |  | ~577projects\fall2016\projects\f16team04\Development\As_Built_Package | Sys:BackEnd | 1224 | 0.68 | 4 | 2.7 | 449.9 | 0.4 | 6.7 | 6.7 | 439.7 | 1 | 8.3 | 7.2 | 351.7 | 1.2 | 10.4 | 7.7 | 281.4 | 1.3
[7 empty] | Alg: Train | 976 | 1.37 | 3.2 | 4.4 | 224 | 0.6
[7 empty] | Alg: Test | 231 | 0.56 | 0.8 | 0.4 | 550.5 | 0.1
[7 empty] | Sys: FrontEnd | 500 | 0.51 | 1.6 | 0.8 | 597.8 | 0.1
5 | fall2016 | f16a_ShareWeb | 8.7 | 1357.2 |  | ~577projects\fall2016\projects\f16team05\teamwebsite\FinalDeliverables | Picture Module | 2200 | 0.62 | 7 | 4.37 | 503 | 0.6 | 6.96 | 6.68 | 632.36 | 1 | 8.7 | 7.16 | 505.89 | 1.2 | 10.87 | 7.67 | 404.71 | 1.4
[7 empty] | Event Module | 1650 | 0.62 | 5.25 | 3.28 | 503 | 0.5
[7 empty] | User Module | 550 | 0.6 | 1.75 | 1.04 | 527.08 | 0.1
6 | fall2016 | f16a_Newlette_Coins | 9.02 | 1407.12 |  | ~577projects\fall2016\projects\f16team06\FD | Login Page | 168 | 0.48 | 0.55 | 0.26 | 637.19 | 0 | 7.22 | 6.83 | 507.71 | 1.1 | 9.02 | 7.32 | 406.17 | 1.2 | 11.28 | 7.85 | 324.93 | 1.4
[7 empty] | Register Page | 273 | 0.48 | 0.89 | 0.43 | 637.19 | 0.1
[7 empty] | Game Page | 1122 | 1.27 | 3.66 | 4.67 | 240.43 | 0.6
[7 empty] | Loading Page | 100 | 0.22 | 0.33 | 0.07 | 1373.93 | 0
[7 empty] | Profile Page | 200 | 0.36 | 0.65 | 0.23 | 860.5 | 0
[7 empty] | Leader Board | 160 | 0.36 | 0.52 | 0.19 | 853.44 | 0
[7 empty] | User Authentication | 310 | 0.71 | 1.01 | 0.72 | 430.74 | 0.1
[7 empty] | Detonate | 462 | 0.69 | 1.51 | 1.03 | 447.43 | 0.1
[7 empty] | Unit Tests | 450 | 0.56 | 1.47 | 0.82 | 546.31 | 0.1
[7 empty] | Game Creation | 420 | 0.43 | 1.37 | 0.6 | 704.75 | 0.1
7 | fall2016 | f16a_Fuppy | 26.2 | 4087.2 |  | ~577projects\fall2016\projects\f16team07\project\FD | Authentication | 1219 | 1.09 | 5.5 | 6 | 202.2 | 0.6 | 20.9 | 9.9 | 194.8 | 2.1 | 26.2 | 10.7 | 155.9 | 2.5 | 32.7 | 11.5 | 124.7 | 2.9
[7 empty] | Search | 1484 | 1.69 | 6.8 | 11.4 | 129.6 | 1.1
[7 empty] | Appointment | 1378 | 1.39 | 6.3 | 8.7 | 158.3 | 0.8
8 | fall2016/spring2017 | s17b_Fokcus |  |  |  | ~577projects\fall2016\projects\f16team08\FD | N/A
9 | fall2016/spring2017 | s17b_FarmWorkers_SafetyApp | 17.5 | 2730 |  | ~577projects\fall2016\projects\f16team09\AsBuilt | User Profile | 1100 | 0.63 | 3.8 | 2.4 | 460 | 0.3 | 14 | 8.5 | 356.8 | 1.6 | 17.5 | 9.1 | 285.4 | 1.9 | 21.9 | 9.8 | 228.3 | 2.2
[7 empty] | Notification | 700 | 0.88 | 2.4 | 2.1 | 331 | 0.2
[7 empty] | Education | 2700 | 1.25 | 9.3 | 11.7 | 231 | 1.3
[7 empty] | Weather | 200 | 1.02 | 0.7 | 0.7 | 283.8 | 0.1
[7 empty] | Farm | 300 | 0.6 | 1 | 0.6 | 484.6 | 0.1
10 | fall2016/spring2017 | s17b_eLockbox | 6 | 936 |  | ~577projects\fall2016\projects\f16team10\FD\2017Spring | Case Management | 1272 | 0.86 | 3.98 | 3.43 | 370 | 0.5 | 4.8 | 6 | 463.88 | 0.8 | 6 | 6.43 | 371.1 | 0.9 | 7.5 | 6.9 | 296.88 | 1.1
[7 empty] | User Management | 328 | 0.82 | 1.03 | 1.03 | 389 | 0.1
[7 empty] | Activity Management | 300 | 0.95 | 0.94 | 0.94 | 338 | 0.1
[7 empty] | System Functions | 328 | 0.82 | 1.03 | 1.03 | 389 | 0.1

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab