## Form Responses 2
Timestamp | Name | Task | Description (Optional) | Week | Effort
2018-02-07 12:41 | Wanting Dong | Learn the introduction of the project. Set up the enviornment. |  | Week#1 1/24-1/31 | 3h
2018-02-07 12:44 | Wanting Dong | Study the current structure used in the project. Write the summary | Including how the structure looks like in JSON file and how to extract it from xmi file. | Week#2 2/1-2/7 | 3h30m
2018-02-07 12:50 | Zhamilya Maksutbekkyzy | Research on building models methods, search for different model building tools and assessing methods. |  | Week#2 2/1-2/7 | I didn't track time, but approximately, around 5-6 hours.
2018-02-07 13:09 | Shengping Yao | Environment setting | Environment setting, get general understanding for the whole project. Meet with the leader. | Week#1 1/24-1/31 | 10H
2018-02-07 13:27 | Xianhe Chen | Integration, deployment, and testing | Got familiar with the environment, set everything up on my local machine. | Week#2 2/1-2/7 | 3 HOURS
2018-02-07 14:36 | Shrushti Patel | Environment Setup |  | Week#1 1/24-1/31 | 5h
2018-02-07 14:37 | Shrushti Patel | Environment Setup and studying database structure |  | Week#2 2/1-2/7 | 6h
2018-02-07 21:31 | Kiranmai Ponakala | Read documentation |  | Week#1 1/24-1/31 | 3
2018-02-09 08:25 | yihao | prepare enviornment |  | Week#3 2/8-2/14 | 4hour
2018-02-09 20:42 | guancheng liu | A sequence diagram is an interaction diagram that shows how objects operate with one another and in what order. A class diagram is a type of static structure diagram that describes the structure of a system by showing the system's classes, their attributes, operations (or methods), and the relationships among objects. The UMLModElementEvaluator.js is to extracting models from the xml files, and then contrstrct a hierarchy of the elements and save them into a json file. The UMLModElementEvaluator.js is output the necessary information from model analysis to model evaluation. |  | Week#2 2/1-2/7 | 5h30m
2018-02-09 22:59 | Atharva Kale | Install environment, Read basics of UML |  | Week#1 1/24-1/31 | 4h00m
2018-02-09 23:02 | Atharva Kale | Install environment, read about feature selection, implement feature selection in R | Also read about statistics to better understand stepwise regression | Week#2 2/1-2/7 | 8h00m
2018-02-11 15:12 | Kiranmai Ponakala | Setting up environment |  | Week#2 2/1-2/7 | 4
2018-02-12 12:50 | Sachin Keshavaiah Lohith | Understanding how UML evaluators and extractors work and generate a brief report on the same |  | Week#2 2/1-2/7 | 4h30m
2018-02-13 10:58 | Vibhanshu Sharma | Created report for UMLModelInfoManagerMongoDB.js to study the database structure and the functions implemented in the .js file. |  | Week#4 2/8-2/14 | 2.5 hour
2018-02-13 11:05 | Vibhanshu Sharma | Visual Paradigm Integration | Studying and understanding the visual paradigm xml file structure to build a integration tool. | Week#3 2/1-2/7 | 3h40m
2018-02-13 11:06 | Mohit Garg | Environment Setup and studying R scripts |  | Week#1 1/24 | 5h30m
2018-02-13 11:07 | Vibhanshu Sharma | Understanding- UMLx | Attended meeting and introductory talk on the project by Kan, to start individual task assigned in respective group. | Week#2 1/25-1/31 | 2h
2018-02-13 11:07 | Mohit Garg | Implementing R script for modelEvaluation.cvs |  | Week#2 1/25-1/31 | 3h15m
2018-02-13 11:08 | Vibhanshu Sharma | Environment Setup | Installing and setting up the environment (node.js and mongodb) | Week#1 1/24 | 1h50m
2018-02-13 11:16 | Anitha Neelakantan | To segregate the ssad lcp documents for 2012-2013 and 2013-2014 |  | Week#4 2/8-2/14 | 5h
2018-02-13 16:59 | Kiranmai Ponakala | Setting up amazon EC2 |  | Week#3 2/1-2/7 | 4
2018-02-13 17:22 | Vaishnavi venkatraman | Setting up the environment and repository | The task was to setup mongodb on our local system and connect to the server following the instructions. | Week#3 2/1-2/7 | 2h30m
2018-02-13 17:25 | Vaishnavi Venkatraman | Categorize past project documents. | Collect and categorize LCP,OCD and SSAD documents from years 2012-2013 and 2013-2014 from the google drive link provided. Copy them to relevant subfolders on the testing branch of git repository and update the file list.xlsx document. | Week#4 2/8-2/14 | 3h30m
2018-02-14 14:29 | Shengping Yao | Learn MongoDB, study the structure of database |  | Week#4 2/8-2/14 | 10h
2018-02-15 12:17 | Traci Yuen | Display the icon images when the user clicks Query Item under Model Info. | The issue was that the useCase.svg file had the path to the icon images as "img/NODE.png". Since there was no img directory present in the same directory as useCase.svg, the icon images didn't load. So I created an "img" directory in the same directory as useCase.svg and copied all the image files to it. The current issue now is the the way I came up with the path to create the directory. I used members that were already present in UMLxServices.js but I had to hardcode the modelID to truncate it to 32 characters. I spent most of my time looking at the files and trying to figure out how they related to one another. Also, trying to understand Javascript and Express.js syntax. | Week#4 2/8-2/14 | 7h
2018-02-16 15:04 | guancheng liu | Attend a meeting and discuss a github issue. spend some time to look at the github issue. |  | Week#4 2/8-2/14 | 4h 30m
2018-02-16 18:17 | Sachin Keshavaiah Lohith | Checking GitHub issues for adding metrics to model evaluator |  | Week#4 2/8-2/14 | 4h30m
2018-02-16 20:39 | Shrushti Shaileshkumar Patel | Decomposing modelInfo DB |  | Week#4 2/8-2/14 | 6h
2018-02-18 19:00 | Atharva Kale | Feature Selection, Lasso Regression, Enterprise Architect | Implement feature selection on modelsEvaluation.csv, Read "A Signifance Test of Lasso" paper and researched onLasso Regression, Installed Enterprise Architect. | Week#4 2/8-2/14 | 13h00m
2018-02-18 19:12 | ANUSHA BILAKANTI | setup environment | Had issues in setup. ut finally resolved it | Week#4 2/8-2/14 | 20 hours
2018-02-18 19:11 | ANUSHA BILAKANTI | modified saveModelInfo |  | Week#5 2/15-2/21 | 12 hours
2018-02-19 00:42 | Zhamilya | Creating diagrams for SSADs and OCDs |  | Week#5 2/15-2/21 | 11h14m
2018-02-19 11:08 | Vibhanshu Sharma | Decomposition of the UML model into three separate models, namely- domain model, uml model and use case model. | Performed decomposition of uml models into three mod os to perform normalisation of the db structure. Used mongo import to push the new object details into the model collection. | Week#5 2/15-2/21 | 4h
2018-02-20 10:28 | Kate Glazko | Understanding why icons are not rendering correctly | Spent time running the example locally and learning about file paths on MacOS to try and see what is wrong. Spent time in Slack seeing other peoples' input and testing their solutions. | Week#4 2/8-2/14 | 3h
2018-02-21 22:49 | Shengping Yao | update method of queryModelInfo() | I helped teammates to understand the database model, to introduce my method, to learn Mongo DB method and Node.js. The difficulties are I can't complete the task by my own, my teammates are also busy, they also can't help me. | Week#5 2/15-2/21 | 40H
2018-02-23 10:13 | Sachin Keshavaiah Lohith | Develop code to log metrics in class diagram - part 1 |  | Week#6 2/22-2/28 | 5h
2018-02-23 20:02 | Shrushti Shaileshkumar Patel | Database decomposition and method update |  | Week#5 2/15-2/21 | 9
2018-02-25 19:04 | Mohit Garg | Make UML diagrams in EA |  | Week#4 2/8-2/14 | 6h00m
2018-02-28 02:24 | Aishwarya Badanidiyoor | Configuration and Setting up | I set it up fine, and noticed that all the graphs were missing | Week#1 1/24 | 4h00m
2018-02-28 02:25 | Aishwarya Badanidiyoor | Learn about graphviz dotty tool | I learnt about how to create graphs and such, but I still couldn't see the graphs even though I tried setting the path manually several times. | Week#2 1/25-1/31 | 4h00m
2018-02-28 02:28 | Aishwarya Badanidiyoor | Run the example test on the UMLx tool | Last week's inability to run the UMLx tool properly affected me trying to run the example test found in the experiments folder as it didn’t work when running the node command. You and I had a discussion about this and you said that was not necessary anymore so we moved past it. | Week#3 2/1-2/7 | 4h30m
2018-02-28 02:29 | Aishwarya Badanidiyoor | Go through specified js files | I went through the js files you mentioned - Umlmodelextractor.js and explored Extractmodelinfo and drawprecedencediagram. | Week#3 2/1-2/7 | 2h00m
2018-02-28 02:33 | Aishwarya Badanidiyoor | Mostly catch up work from having injured my foot and missing the meeting | I was trying to catch up at this point because I STILL couldnt get the UMLx tool to display graphs. I had added the output and uploads folder into public but things were still not working, I also included "fs-extra" as I realized that was missing for me. | Week#4 2/8-2/14 | 4h00m
2018-02-28 02:36 | Aishwarya Badanidiyoor | Collaborative Task - fix the image icon issue; get graphs to show. | I have to admit, Traci did most of the work here. Again, working together was out of the question as I was not able to come to campus because of my foot and Kate was also a DEN student, so off-campus. I FINALLY got the graphs working after installing fs-extra and mongodb to downgrade from 3.6 to 3.4. | Week#5 2/15-2/21 | 4h00m
2018-02-28 02:38 | Aishwarya Badanidiyoor | Generate dotty graph for Analysis Diagram | I got this to work, but with some issues. I do think there were problems with the fs.writeFile function as it kept overwriting and rewriting characters and sets of characters over my dotty file. I tried using a lock file which didnt work. But i have sent in what I have so far. | Week#6 2/22-2/28 | 7h00m
2018-02-28 17:13 | Traci Yuen | Created dotty graph of activity diagram. |  | Week#6 2/22-2/28 | 10h0m
2018-03-02 18:44 | Shengping Yao | update queryModelInfo |  | Week#6 2/22-2/28 | 20h
2018-03-02 23:28 | Shrushti Shaileshkumar Patel | Update DeleteModel method |  | Week#6 2/22-2/28 | 6
2018-03-03 13:43 | ANUSHA BILAKANTI | The database structure was changed. So had to modify the saveInfoModel() and test it. Created a dummy ModelInfo object for testing purposes |  | Week#7 3/1-3/7 | 10 hours
2018-03-03 23:14 | Sachin Keshavaiah Lohith | Get the model evaluator to work |  | Week#7 3/1-3/7 | 4h
2018-03-04 09:35 | Vibhanshu Sharma | UpdateModelInfo(), updateDomainModelInfo() and updateUseCaseInfo() function | Updating the above functions based on the database structure that was created previously(2_25) to the new database structure of 2_27. | Week#11 3/29-4/4 | 5h30m
2018-03-04 12:56 | Wanting Dong | Learn different metrics of different UML diagrams |  | Week#4 2/8-2/14 | 4h
2018-03-04 12:57 | Wanting Dong | add metrics of class diagram | modify UMLModelElementEvaluator.js | Week#5 2/15-2/21 | 3h
2018-03-04 12:58 | Wanting Dong | add metrics of class diagram and test |  | Week#6 2/22-2/28 | 8h
2018-03-05 09:51 | Atharva Kale | UML Models, Feature Selection using LASSO | Created UML Models using Enterprise Architect, Researched and wrote summary for "Feature Selection using LASSO" | Week#6 2/22-2/28 | 11 h
2018-03-06 18:15 | Zhamilya Maksutbekkyzy | Building Uml diagrams, research on Lasso, performing k-folds cross validation |  | Week#7 3/1-3/7 | 9
2018-03-08 20:47 | Shrushti Shaileshkumar Patel | Added deleteRepo method |  | Week#7 3/1-3/7 | 5
2018-03-09 09:41 | Vibhanshu Sharma | Update RepoInfo Collection function | Made changes in the updateRepoInfo() function according to the example database structure posted on github. Also, made followup changes in updateModelInfo() functions. | Week#8 3/8-3/14 | 3h25m
2018-03-09 11:11 | Sachin Keshavaiah Lohith | Implement class diagram parser and calculate corresponding metrics |  | Week#7 3/1-3/7 | 9h
2018-03-10 00:12 | ANUSHA BILAKANTI | I recreated queryRepoInfo() function |  | Week#8 3/8-3/14 | 10 hours
2018-03-16 11:04 | Sachin Keshavaiah Lohith | Spring break |  | Week#9 3/15-3/21 | 2h
2018-03-18 13:57 | Atharva Kale | Model Selection by Cross Validation, Statistics Output in R | Applying cross validation based on feature selection using LASSO. Output statistics in JSON format using R. | Week#7 3/1-3/7 | 11h00m
2018-03-19 18:58 | Traci Yuen | Fixing activity diagram dotty graph & highlight activities |  | Week#13 4/12-4/18 | 8h
2018-03-23 10:57 | Sachin Keshavaiah Lohith | Debugging CSV file generation |  | Week#10 3/22-3/28 | 5h
2018-03-24 11:47 | Shrushti Patel | Created functions to save estimations |  | Week#9 3/15-3/21 | 8
2018-03-24 16:33 | ANUSHA BILAKANTI | created function queryRepoInfoByPage() | created function queryRepoInfoByPage() for pagination using stepParamter, pageParameter; used skip and limit | Week#10 3/22-3/28 | 10
2018-03-26 14:14 | Vibhanshu Sharma | Creating an RESTful API to call updateModelInfo() |  | Week#10 3/22-3/28 | 4h40min
2018-03-27 07:41 | Atharva Kale | Evaluation of LASSO method with MMRE & PRED | Evaluating the LASSO method by cross validation with MMRE and PRED metrics | Week#9 3/15-3/21 | 12h
2018-03-27 10:22 | Zhamilya | Building diagrams, implementation of CV |  | Week#10 3/22-3/28 | 9
2018-03-27 10:23 | Zhamilya | Cross Validation implementation, learning glmnet on R |  | Week#8 3/8-3/14 | 8,5
2018-03-27 10:57 | Shengping Yao | UI modification |  | Week#9 3/15-3/21 | 10H
2018-03-27 10:58 | Shengping Yao | UI modification | change tabs, add buttons | Week#10 3/22-3/28 | 10H
2018-03-28 10:53 | Wanting Dong | add metrics into csv file and learn visual paradigm |  | Week#7 3/1-3/7 | 5h
2018-03-28 10:57 | Wanting Dong | fix github uploading issue | make sure that all modified codes are passed the test and are uploaded on the github | Week#8 3/8-3/14 | 2h30
2018-03-28 10:58 | Wanting Dong | add sequence parser for visual paradigm |  | Week#9 3/15-3/21 | 5h15
2018-03-28 11:01 | Wanting Dong | update the sequence parser | add function to deal with more situation of the diagram. test csv file in previous work | Week#10 3/22-3/28 | 4h
2018-03-28 13:37 | Lingquan | implement class diagram method |  | Week#9 3/15-3/21 | 6h20m
2018-03-28 21:35 | guancheng liu | Integrate a list of metrics | Study the metrics and figure out how to integrate | Week#3 2/1-2/7 | 7h
2018-03-28 21:37 | guancheng liu | Have a discussion on the metrics |  | Week#4 2/8-2/14 | 5h20m
2018-03-28 21:39 | guancheng liu | GetGet familiar with different diagram parsers. |  | Week#5 2/15-2/21 | 6h
2018-03-28 21:41 | guancheng liu | Get familiar with different diagram parsers and Write a summary of 100 words (should be precise) about the input, output. |  | Week#6 2/22-2/28 | 6h
2018-03-28 21:42 | guancheng liu | Integrate the parser into the framework | do further testing on the integration, for example, the metrics should be put into the corresponding objects (modelinfo, usecaseinfo, domainModel). | Week#7 3/1-3/7 | 6h
2018-03-28 21:43 | guancheng liu | Integrate the parser into the framework | Output the derived data into csv files and study the xml files exported from visual paradigm. | Week#8 3/8-3/14 | 6h
2018-03-28 21:44 | guancheng liu | Write simple parpers based on XMI files exported from Visual Paradigm. |  | Week#9 3/15-3/21 | 9h
2018-03-28 21:44 | guancheng liu | Write simple parpers based on XMI files exported from Visual Paradigm. |  | Week#10 3/22-3/28 | 6h
2018-03-29 08:46 | yihao | research how to find lambda for Lasso |  | Week#8 3/8-3/14 | 5h
2018-03-29 08:47 | yihao | create models |  | Week#10 3/22-3/28 | 3h
2018-03-29 08:49 | yihao | create models |  | Week#8 3/8-3/14 | 5h
2018-03-29 08:50 | yihao | build regression models |  | Week#7 3/1-3/7 | 4h
2018-03-29 08:50 | yihao | reading materials about Lasso |  | Week#6 2/22-2/28 | 3h
2018-03-29 08:55 | yihao | reading 《significant test for Lasso》 |  | Week#5 2/15-2/21 | 2
2018-03-29 20:00 | Shrushti Shaileshkumar Patel | Create functions to modify model estimation |  | Week#10 3/22-3/28 | 5
2018-04-02 09:36 | Vibhanshu Sharma | Implement Pagination in Jade template | Creating a RestAPI to implement pagination in UMLx tool. | Week#11 3/29-4/4 | 8h45min
2018-04-02 10:36 | Yekaterina (Kate) Glazko | I found >50 Apache open source projects and their languages and whether or not they had time-tracking | This could be automated in the future with Selenium but there were several instances of re-captcha | Week#11 3/29-4/4 | 6 h
2018-04-02 10:45 | Yekaterina (Kate) Glazko | Find at least 10 open source projects that are not from Apache and link to their Jira | This was not easy because Atlassian took down their page with all the open source projects so I did manually search the internet | Week#10 3/22-3/28 | 5h
2018-04-02 10:53 | Yekaterina (Kate) Glazko | Write a summary of sequence diagram work to share with the team | Since my diagram was not correct, I put together my learnings in a document that could be shared with the rest of the team. | Week#9 3/15-3/21 | 5h
2018-04-02 10:54 | Yekaterina (Kate) Glazko | Fix diagram from previous week | I tried to implement a correct sequence diagram with Dotty and failed. I tried to understand sequence diagrams more. I began setting up PlantUML. | Week#8 3/8-3/14 | 8h
2018-04-02 10:58 | Yekaterina (Kate) Glazko | Make sequence diagram | I tried to make my sequence diagram better since it did not receive a great completion score. I spent many hours digging through the sample XML file and cross-checking it with the sample image we received to understand why mine wasn't showing the "activities" it needed to show. | Week#8 3/8-3/14 | 7h30m
2018-04-02 11:00 | Yekaterina (Kate) Glazko | Sequence Diagram Attempt #1 Pt. 2 | I incorrectly made a sequence diagram that looked more like an activity diagram linking messages together. I learned how to make the Dotty graph horizontal and how to make the nodes of the graph different colors. I am also not as familiar with JS as I would like to be so I spent time looking up syntax. | Week#7 3/1-3/7 | 5h
2018-04-02 11:01 | Yekaterina (Kate) Glazko | Sequence Diagram Pt. 1 | I spent some trying to understand what a sequence diagram is and what it should do. I was confused by all the different Google Search results and how the diagrams were varied in both content and appearance. | Week#6 2/22-2/28 | 4h
2018-04-02 12:01 | Yekaterina (Kate) Glazko | Incorporate fixes into own branch | Incorporate Tracy's fix into my own branch and make the icons show, also debug some issues preventing running on latest Mac OS X | Week#6 2/22-2/28 | 4h
2018-04-02 18:21 | ANUSHA BILAKANTI | create repoDetail function | It takes repoId as parameter. Finds the modelInfo's with those repoId. Finds the sum of NT (field in TransactionAnalysis) for all these modelInfo's. Creates a collection noOfTransactions with fiels: _id, rep_id, NT(sum), timestamp(time document is created) | Week#11 3/29-4/4 | 10
2018-04-03 17:19 | Traci Yuen | Integrating highlight function and separating graph function for activity diagram |  | Week#10 3/22-3/28 | 10h
2018-04-03 23:15 | Zhamilya | modify the current R script: linearRegression: EUCP-EXUCP-DUCP.R to save some meta-data about the trained model. | Specifically, the number of data points used for training and testing. | Week#11 3/29-4/4 | 8h30m
2018-04-04 21:01 | Zhamilya | Building UML diagrams |  | Week#10 3/22-3/28 | 7h
2018-04-06 12:12 | Sachin Keshavaiah Lohith | Write activity diagram parser for visual paradigm and fix errors in old code |  | Week#12 4/5-4/11 | 10h
2018-04-09 01:22 | Shrushti Shaileshkumar Patel | Fixed queryrepoinfo and modifyModelCharacteristics |  | Week#11 3/29-4/4 | 6
2018-04-09 19:31 | ANUSHA BILAKANTI | tested saveInfoModel, queryRepoInfo(), queryRepoInfoByPage(), completed function noOfTransactions | tested saveInfoModel, queryRepoInfo(), queryRepoInfoByPage(), completed function noofTransactions to ensure that if a doc with today's timestamp is already present, then new doc with same timestamp will not be inserted; collected few github links(https://github.com/flyqk/UMLx/issues/232) | Week#12 4/5-4/11 | 10
2018-04-12 15:35 | Shrushti Shaileshkumar Patel | Fix querymodelInfo method, deleteModel and saveModelInfoCharacteristics |  | Week#12 4/5-4/11 | 6
2018-04-13 10:34 | Sachin Keshavaiah Lohith | Optimize activity diagram parser |  | Week#13 4/12-4/18 | 7h
2018-04-13 11:56 | Vibhanshu Sharma | List the Repos in User Info page in toolbar. | List the repos that are associated with a user in the user page. | Week#13 4/12-4/18 | 5h
2018-04-13 11:58 | Vibhanshu Sharma | Implemented pagination on projects uploaded by the user. | Created NodeJS API and JavaScript function to fetch the models data and make the AJAX call to the API respectively. Also, implemented pagination in jade to show consistent number of objects in each page in UMLx tool. | Week#12 4/5-4/11 | 11h
2018-04-13 14:23 | Traci | Integrate Activity Diagram graph and highlight function into webpage. |  | Week#12 4/5-4/11 | 10h
2018-04-13 15:47 | Zhamilya | Building new uml diagrams, fixing r code with metadata. |  | Week#12 4/5-4/11 | 7h
2018-04-15 12:39 | Kate Glazko | Pages 14-19 of Apache projects |  | Week#13 4/12-4/18 | 5h30m
2018-04-15 12:41 | Kate Glazko | Pg 11-13 Apache projects |  | Week#12 4/5-4/11 | I forget but between 4h-5h
2018-04-17 18:35 | Kiranmai Ponakala | Data Collection on github |  | Week#5 2/15-2/21 | 5
2018-04-17 18:35 | Kiranmai Ponakala | Data Collection on github |  | Week#6 2/22-2/28 | 5h
2018-04-17 18:35 | Kiranmai Ponakala | Data Collection |  | Week#7 3/1-3/7 | 5h
2018-04-17 18:36 | Kiranmai Ponakala | Data collection |  | Week#8 3/8-3/14 | 5h
2018-04-17 18:36 | Kiranmai Ponakala | Data Collection |  | Week#9 3/15-3/21 | 5h
2018-04-17 18:37 | Kiranmai Ponakala | Data Collection |  | Week#10 3/22-3/28 | 5h
2018-04-17 18:37 | Kiranmai Ponakala | Data Collection |  | Week#11 3/29-4/4 | 5h
2018-04-17 18:37 | Kiranmai Ponakala | Data Collection |  | Week#12 4/5-4/11 | 5h
2018-04-17 18:38 | Kiranmai Ponakala | Data Collection |  | Week#12 4/5-4/11 | 5h
2018-04-17 18:38 | Kiranmai Ponakala | Data Collection |  | Week#13 4/12-4/18 | 5h
2018-04-17 18:40 | Kiranmai Ponakaa | Data Collection |  | Week#14 4/19-4/25 | 5h
2018-04-18 00:09 | ANUSHA BILAKANTI | completed function noofTransactions by adding fields UseCaseNum, EntityNum and tested tested saveInfoModel, queryRepoInfo(), queryRepoInfoByPage() | completed function noofTransactions by adding fields UseCaseNum, EntityNum and tested tested saveInfoModel, queryRepoInfo(), queryRepoInfoByPage() | Week#13 4/12-4/18 | 10
2018-04-18 00:37 | Zhamilya | UML diagrams building |  | Week#13 4/12-4/18 | 11h
2018-04-21 18:23 | Vibhanshu Sharma | Verify the previous task on the merged branch and update pagination on the modified API |  | Week#14 4/19-4/25 | 5h
2018-04-21 18:28 | Vibhanshu Sharma | Created Profile page on front end with details of RepoInfo |  | Week#13 4/12-4/18 | 3h50m
2018-04-22 11:16 | Traci Yuen | Integrating activity diagram to toggle and parsing sequence diagram into plantUML format |  | Week#13 4/12-4/18 | 10h
2018-04-23 20:05 | Shrushti Shaileshkumar Patel | fixed saveModelInfoCharacteristics |  | Week#13 4/12-4/18 | 5
2018-04-24 15:09 | Kate Glazko | Open source projects 14-19 | Collecting pages 14-19 of the open source projects | Week#13 4/12-4/18 | 6.5h
2018-04-25 21:55 | Kate Glazko | Collect COCOMO ratings | Collect COCOMO ratings for 2011-17 | Week#14 4/19-4/25 | 8h20m
2018-04-25 22:01 | Shengping Yao | Complete task of add Archive tab, and add more features according to assignment. |  | Week#14 4/19-4/25 | 30h
2018-04-25 22:01 | Traci Yuen | Study the model drawers and dotty language |  | Week#1 1/24 | 8h
2018-04-25 22:01 | Shengping Yao | Fixed bugs, developed Archive tabs |  | Week#13 4/12-4/18 | 25h
2018-04-25 22:02 | ANUSHA BILAKANTI | getting to know about project | getting to know about project | Week#1 1/24 | 10
2018-04-25 22:02 | Traci Yuen | Study the model drawers and dotty language |  | Week#2 1/25-1/31 | 10h
2018-04-25 22:02 | ANUSHA BILAKANTI | getting to know about project | getting to know about project | Week#2 1/25-1/31 | 10
2018-04-25 22:02 | Shengping Yao | Tried several solution for Archive tabs, add features according to assignment | Wrong direction, go back to right way after meeting | Week#12 4/5-4/11 | 25h
2018-04-25 22:03 | ANUSHA BILAKANTI | getting to know about project | getting to know about project | Week#4 2/8-2/14 | 10
2018-04-25 22:03 | ANUSHA BILAKANTI | understanding the existing database structure and writing about it | understanding the existing database structure and writing about it | Week#5 2/15-2/21 | 10
2018-04-25 22:04 | Traci Yuen | Study the model drawers and dotty language, process of generating visualizations, running the code | (Hi Kan, I accidentally put the tasks for Week #1 and #2 as the one for Week #3. During Weeks #1 and #2, I was reading over the code, setting up the environment, and reviewing UML diagrams.) | Week#3 2/1-2/7 | 10h
2018-04-25 22:04 | ANUSHA BILAKANTI | restructured existing database structure | restructured existing database structure | Week#6 2/22-2/28 | 10
2018-04-25 22:05 | Traci Yuen | Worked on showing the icons of the diagrams on the webpage. |  | Week#4 2/8-2/14 | 10h
2018-04-25 22:07 | Traci Yuen | Getting icons to show and start to work on creating the activity diagram and producing a dotty file |  | Week#5 2/15-2/21 | 10h
2018-04-25 22:07 | Traci Yuen | Worked on creating the activity diagram and producing a dotty file |  | Week#6 2/22-2/28 | 10h
2018-04-25 22:09 | Traci Yuen | Continued on visualization of diagram, highlight diagram |  | Week#7 3/1-3/7 | 10h
2018-04-25 22:10 | Traci Yuen | Continued to work on visualization of activity diagram and fixing highlight method to work with embedded SVG document |  | Week#8 3/8-3/14 | 10h
2018-04-25 22:11 | Traci Yuen | Continued work on visualization of activity diagram -- mostly integration into current code |  | Week#9 3/15-3/21 | 10h
2018-04-25 22:11 | Traci Yuen | Fixed activity diagram (made lines straight, made nodes fixed size, made arrowheads different) |  | Week#10 3/22-3/28 | 8h
2018-04-25 22:12 | Traci Yuen | Testing my generated activity diagram with different examples and fixing it |  | Week#11 3/29-4/4 | 10h
2018-04-25 22:14 | Traci Yuen | Generated 5 XML files of activity diagrams to test with and worked to integrate code into current structure |  | Week#12 4/5-4/11 | 10h
2018-04-25 22:15 | Traci Yuen | Make activity diagram display onto webpage and make sure it is correct, add highlight function |  | Week#13 4/12-4/18 | 10h
2018-04-25 22:16 | Traci Yuen | Last fixes to have activity diagram properly display on webpage when toggled, fixed highlight function to clear others first, created JSON parser for PlantUML sequence diagrams |  | Week#14 4/19-4/25 | 10h
2018-04-25 22:52 | Atharva Kale | Generate UML models and final report |  | Week#14 4/19-4/25 | 13h
2018-04-25 22:52 | Atharva Kale | Generate UML Models |  | Week#13 4/12-4/18 | 12h30m
2018-04-25 23:09 | Atharva Kale | Generate UML models, effort prediction result in json format , core task | Core task: plot lambda vs mmre, pred and mse as cross validation results | Week#12 4/5-4/11 | 14h00m
2018-04-25 23:19 | Atharva Kale | Integrate Lambda sequence function, Evaluate CV with MMRE & PRED | Integrate Lambda sequence function in Rscript and perform cross validation to evaluate with MMRE & PRED | Week#11 3/29-4/4 | 11h00m
2018-04-25 23:36 | Atharva Kale | Calculate statistics on json format |  | Week#10 3/22-3/28 | 11h0m
2018-04-25 23:50 | Sachin Keshavaiah Lohith | Parse all required nodes in the activity diagram |  | Week#13 4/12-4/18 | 9h
2018-04-25 23:50 | Sachin Keshavaiah Lohith | Parse all required nodes in the activity diagram |  | Week#14 4/19-4/25 | 8h
2018-04-26 07:21 | Anitha Neelakantan | added trending line chart, added button for all the tables and fixed small bugs after integration |  | Week#14 4/19-4/25 | 15
2018-04-26 07:22 | Anitha Neelakantan | updated the code for generating the tables and started working on trending line chart |  | Week#13 4/12-4/18 | 15
2018-04-26 07:24 | Anitha Neelakantan | collected cocomo data 2011-2012, 2015-2016, 2016-2017, resolved issues with git and code for the previous week |  | Week#12 4/5-4/11 | 15
2018-04-26 07:26 | Anitha Neelakantan | create tables based on json generated |  | Week#11 3/29-4/4 | 15
2018-04-26 07:29 | Anitha Neelakantan | worked on displaying data based on the statistical item clicked |  | Week#9 3/15-3/21 | 15
2018-04-26 07:31 | Anitha Neelakantan | worked on fixing the issue of the histogram not seen by going through code and understanding the flow |  | Week#8 3/8-3/14 | 15
2018-04-26 07:33 | Anitha Neelakantan | parsed usecase evaluation csv to create chart |  | Week#6 2/22-2/28 | 15
2018-04-26 07:34 | Anitha Neelakantan | Merge the distributions into one using highchart |  | Week#5 2/15-2/21 | 15
2018-04-26 07:36 | Anitha Neelakantan | locate the relevant files from project repository and create catalog for the project folder for all the years |  | Week#4 2/8-2/14 | 15
2018-04-26 07:38 | Anitha Neelakantan | Went through code |  | Week#3 2/1-2/7 | 10
2018-04-26 07:39 | Anitha Neelakantan | Set up everything for the project. |  | Week#2 1/25-1/31 | 5h
2018-04-26 11:28 | Lingquan Han | being familiar with the project |  | Week#1 1/24 | 5h20m
2018-04-26 11:28 | Lingquan Han | set up enviorment |  | Week#2 1/25-1/31 | 5h40m
2018-04-26 11:29 | Lingquan Han | learn dot and graphviz |  | Week#3 2/1-2/7 | 5h10m
2018-04-26 11:30 | Lingquan Han | hard code for generate class diagram |  | Week#4 2/8-2/14 | 6h
2018-04-26 11:32 | Lingquan Han | create generate_class_diagram function |  | Week#5 2/15-2/21 | 6h20m
2018-04-26 11:33 | Lingquan Han | debug the generate_class_function |  | Week#6 2/22-2/28 | 5h50m
2018-04-26 11:34 | Lingquan Han | learn svg file and merge it into html |  | Week#7 3/1-3/7 | 5h20m
2018-04-26 11:35 | Lingquan Han | hard code of highlight element function |  | Week#8 3/8-3/14 | 5h10m
2018-04-26 11:36 | Lingquan Han | debug highlightElement function |  | Week#9 3/15-3/21 | 6h
2018-04-26 11:38 | Lingquan Han | merge highlightElement fucntion with current project |  | Week#10 3/22-3/28 | 6h30m
2018-04-26 11:39 | Lingquan Han | create 5 domain model and class diagrams | learn EA | Week#11 3/29-4/4 | 6h
2018-04-26 11:39 | Xianhe Chen | Front End | front end work on the team website, diagrams displays, utilities, adjustments, etc. | Week#14 4/19-4/25 | average of 15 hours a week
2018-04-26 11:40 | Lingquan Han | test class diagram and highlight function by the five models of last task |  | Week#12 4/5-4/11 | 6h20m
2018-04-26 11:42 | Lingquan Han | Read the materials for creating visualization of sequence diagrams. and create examples for visualizing sequence diagram. |  | Week#13 4/12-4/18 | 5h
2018-04-26 11:43 | Lingquan Han | integrate code with kqi and debug if problems |  | Week#14 4/19-4/25 | 6h10m
2018-04-26 12:57 | Shrushti Shaileshkumar Patel | Fixed population of modelInfo page |  | Week#14 4/19-4/25 | 5
2018-04-26 13:45 | Zhamilya Maksutbekkyzy | 2012-2013 OCDs UML diagrams |  | Week#14 4/19-4/25 | 10
2018-04-26 15:35 | Vaishnavi Venkatraman | Add a use case distribution chart to the effort estimation result section, | Along with aking minor changes to the charts and adding the distribution chart, we worked on completing the updated requirements of Issue #265 on GitHub. | Week#14 4/19-4/25 | 8h
2018-04-26 15:42 | Vaishnavi Venkatraman | Improve the data api for the trending line at the home page Issue #237 |  | Week#13 4/12-4/18 | 9h30m
2018-04-26 15:45 | Vaishnavi Venkatraman | collect cocomo data for 2011-2012, 2015-2016, 2016-2017 #233, Made minor changes to the charts | Apart from data collection we also worked on resolving the merge conflicts with our repository on GitHub. | Week#12 4/5-4/11 | 10h
2018-04-26 15:48 | Vaishnavi Venkatraman | connect the output statistics with the displays of analytical items. Issue #216 |  | Week#11 3/29-4/4 | 9h
2018-04-26 15:50 | Vaishnavi Venkatraman | Collect cocomo's cost estimations for 2013-2014 #212 | Also worked on binding the data given with the statistical data and charts. | Week#10 3/22-3/28 | 10h
2018-04-26 15:54 | Vaishnavi Venkatraman | After creating the required api, we continued working on Issue#198 | Worked on the updated issue from the previous week, fixed the existing problems and pushed the code to git. | Week#9 3/15-3/21 | 9h
2018-04-26 15:55 | Vaishnavi Venkatraman | create function to request distribution data for the metrics from the backend. #198 |  | Week#8 3/8-3/14 | 10h
2018-04-26 15:58 | Vaishnavi Venkatraman | Worked on parsing the csv files and get data from individual columns. |  | Week#7 3/1-3/7 | 9h
2018-04-26 16:00 | Vaishnavi Venkatraman | Merge the distributions into one using highchart. Issue #168 |  | Week#6 2/22-2/28 | 9h
2018-04-26 16:02 | Vaishnavi Venkatraman | categorize other folders (except for 2012-2013, 2013-2014, and 2014-2015) for LCP,OCD and SSAD |  | Week#5 2/15-2/21 | 10h
2018-04-26 16:03 | Vaishnavi Venkatraman | locate the relevant files from project repository and create catalog for the project folder Issue #154 |  | Week#4 2/8-2/14 | 9h
2018-04-26 16:04 | Vaishnavi Venkatraman | Setting up the project and understanding how the data is generated to high charts |  | Week#3 2/1-2/7 | 10h
2018-04-26 17:43 | guancheng liu | work on the issue and solve the problems left |  | Week#12 4/5-4/11 | 4h
2018-04-26 17:43 | guancheng liu | work on the issue and solve the problems left |  | Week#13 4/12-4/18 | 6h
2018-04-26 17:43 | guancheng liu | work on the issue and solve the problems left |  | Week#14 4/19-4/25 | 6h
2018-04-26 17:44 | guancheng liu | work on the issue and solve the problems left |  | Week#14 4/19-4/25 | 5h
2018-04-26 18:34 | Aishwarya Badanidiyoor | Get the program to output a robustnessdiagram.dotty | The output of the dotty file kept garbling a few characters - submitted in the homework slack channel - it was consistently happening in the same row and column of the dotty file. Once i manually corrected those two characters the robustness diagram was displayed properly. This garbling was happening probably because multiple writes were happening to this file. | Week#6 2/22-2/28 | 12h00m
2018-04-26 18:39 | Aishwarya Badanidiyoor | Correct the garbling issue and display a properly formatted diagram | While using graphViz I finally got the graph to display correctly. However, there was miscommunication -- I was told that analysis diagrams and robustness diagrams were the same -- so I basically wrote a function to create an analysis diagram identical to the one shown on the existing tool. I was then told that this wasn't correct and realized there had been a communication gap -- apparently they were only similar in the sense that they used the same parsers. | Week#7 3/1-3/7 | 09h00m
2018-04-26 18:46 | Aishwarya Badanidiyoor | Correct the function to display Robustness Diagram (instead of analysis diagram) | I got the robustness diagram to display correctly. I hit a few bumps along the way, because I was under the impression that the parser for analysis and robustness diagrams would be the same and therefore the activities and precedence relations would be re-usable. However, that was not the case. I informed Kan and he told me I could define a JSON structure of the activities and precedence relations - ie just assume that this hardcoded JSON structure is the output of the parser and use it to visualize the diagram. Once I did this, it was pretty easy from there. | Week#8 3/8-3/14 | 12h00m
2018-04-26 18:48 | Aishwarya Badanidiyoor | Add highlight functionality to the robustness diagram generated | This was confusing for me at first because I didnt know if I had to create an HTML page or not - I didnt know where else or how else to display it, so I created an HTML page and embedded the svg file in it. I used javascript for the highlighting of the node elements. | Week#9 3/15-3/21 | 09h00m
2018-04-26 18:58 | Aishwarya Badanidiyoor | Add highlight functionality to elements of "Activities" and "Paths" list | i created a table with activities and edges listed out and applied the highlight functionality such that when something in the list was clicked, that element would be highlighted in the diagram. This was still in an html page. | Week#10 3/22-3/28 | 09h00m
2018-04-26 19:01 | Aishwarya Badanidiyoor | Integrate highlighting functionality into scripts.js | I tried working with this for a long time but I don't think I had any fruitful results as I had no way of testing if it would work. scripts.js was for elements and diagram already being displayed on the tool and mine was not displayed yet. | Week#11 3/29-4/4 | 07h00m
2018-04-26 19:05 | Aishwarya Badanidiyoor | Re-organize the code and correct errors after integration; have the file output into the correct repository | I had done this a few times earlier but every time there was an integration there were issues with the diagram display so I had to change it after the parser for robustness diagram was added in by Kan. | Week#12 4/5-4/11 | 11h00m
2018-04-26 19:08 | Aishwarya Badanidiyoor | Get the robustness diagram to display in the tool; add the highlighting functionality | This took some time because the garbling text issue returned after the new robustness parser was added in. I had to create a write lock to make sure the file was not being overwritten with some other unnoticed writes, and it finally solved the issue. This took a long time. But once this was done, I had to change a few things in the jade file and it worked properly after that. I also had to incorporate the highlighting function into the pre-existing list and this took time as well because the list was output from the analysis parser - so I ahd to split up certain node IDs in order to be able to highlight edges. I was told not to bother with highlighting elements. | Week#13 4/12-4/18 | 15h00m
2018-04-26 19:26 | Zhamilya | Explore project, set up github account | learning R, running the application, making research in ML algorithms | Week#1 1/24 | 8h
2018-04-26 19:28 | Zhamilya | Solving issues with MongoDB, learning more about Machine learning | Continue experimenting with the tool, and learning R. Also, fixing problems with Mongo DB | Week#3 2/1-2/7 | 9h
2018-04-26 19:29 | Zhamilya | UML diagrams building |  | Week#4 2/8-2/14 | 9,5 h
2018-04-26 19:31 | Zhamilya | Model selection by cross validation |  | Week#6 2/22-2/28 | 10h
2018-04-26 19:33 | Zhamilya | UML diagrams+extra tasks from github |  | Week#9 3/15-3/21 | 11h
2018-04-28 11:43 | Wanting Dong | Updata SequenceDiagramParser | test on more examples and modify parser | Week#11 3/29-4/4 | 3h
2018-04-28 11:44 | Wanting Dong | Updata SequenceDiagramParser | Correct Precedence Relation of the parser | Week#11 3/29-4/4 | 6h30m
2018-04-28 11:46 | Wanting Dong | Updata SequenceDiagramParser | Add Combined Fragment Judgement in the parser | Week#13 4/12-4/18 | 8h
2018-04-28 11:47 | Wanting Dong | Update SequenceDiagramParser | Uniform the interface of the parser. Modify combined fragment part | Week#14 4/19-4/25 | 4h
2018-04-29 19:43 | Mohit Garg | Setup |  | Week#1 1/24 | 4h30m
2018-04-29 19:44 | Mohit Garg | Setup and stepwise regression |  | Week#2 1/25-1/31 | 4h
2018-04-29 19:45 | Mohit Garg | Stepwise Regression |  | Week#3 2/1-2/7 | 5h10m
2018-04-29 19:45 | Mohit Garg | Script for Multiple regression |  | Week#4 2/8-2/14 | 6h20m
2018-04-29 19:46 | Mohit Garg | UML Model using EA | Learned EA and created few models | Week#5 2/15-2/21 | 4h40m
2018-04-29 19:47 | Mohit Garg | Studied LASO and UML Models |  | Week#7 3/1-3/7 | 7h30m
2018-04-29 19:48 | Mohit Garg | Created script for LASO and UML Models |  | Week#7 3/1-3/7 | 6h
2018-04-29 19:48 | Mohit Garg | Created Script for Multiple Regression for LASO and created UML Models |  | Week#8 3/8-3/14 | 6h30m
2018-04-29 19:49 | Mohit Garg | UML Models and Spring Break |  | Week#9 3/15-3/21 | 5h20m
2018-04-29 19:50 | Mohit Garg | Multiple Regression and Cross Validation. Also created UML Models |  | Week#10 3/22-3/28 | 6h40m
2018-04-29 19:51 | Mohit Garg | Github task for storing meta data and UML Models |  | Week#11 3/29-4/4 | 6h10m
2018-04-29 19:52 | Mohit Garg | Report for LASO and UML Diagrams |  | Week#12 4/5-4/11 | 5h30m
2018-04-29 19:53 | Mohit Garg | UML Models and checking GitHub for missing models |  | Week#13 4/12-4/18 | 4h
2018-04-29 19:54 | Mohit Garg | Multiple Regression for new data and UML Models |  | Week#14 4/19-4/25 | 8h40m
2018-05-04 21:11 | Aishwarya Badanidiyoor | Work on highlight functionality for nodes of analysis diagram, change the icons, generate plantUML for designated example | This technically took two weeks because I had to travel to India in the middle. I sent in the rest of the example XML docs before leaving (i think). I also worked on the plantUML task and submitted that too. After I got to India I had to include changes in my highlight functionality to work on nodes of analysis diagram. This should have taken only five minutes - but because the internet connection in India is so slow it took a really long time for me to set up a fresh copy of the updated project. This fresh copy didn't work so I had to redownload it a few times to see what was going on. I found some strange merge conflict type error in the mondodb manager .js file. I commented out a couple of lines and then it started to work. I finally added the highlight functionality however because of the way the Jade file had been set up, I would need to change the UseCafeInfo.DiagramType = Robustness_diagram to analysis_diagram in order for analysis diagram nodes to highlight. Since the robustness diagram function was inside the analysis diagram function , this would mean that toggle diagram would not show the robustness diagram if I made that change. So I ahve informed Kan and sent in screenshots to describe what I mean. I have only made changes to the scripts.js highlight function. And nothing else, as I don't want to tamper with his existing code and structure. I also changed the icons of the diagram. | Week#14 4/19-4/25 | 25h00m

## Form Responses 1
Timestamp | Name | Task | Week | Effort | Description (Optional)
2017-09-23 20:51 | Upendra Sandeep | Environment set up and walk through | Week#1 | 3hr
2017-09-23 20:55 | Upendra Sandeep | Issue 10- Activity Diagram parsing | Week#2 | 8hrs
2017-09-24 19:18 | Vipin Dwivedi | Parsing XML output from Visual Paradigm. #12 | Week#2 | 4.5hrs
2017-09-24 19:19 | Vipin Dwivedi | Install Visual Paradigm, Get the app running | Week#1 | 3hrs
2017-09-26 13:39 | Sparshith Nairbalige Rai | #9 : Change the links at the bottom of the tab: RepoAnalytics/Analytics into buttons, #8: improve the projects list | Week#2 | 8hrs
2017-09-26 13:39 | Sparshith Nairbalige Rai | #22: create the file selection dialog to upload empirical data for use cases. | Week#3 | 10hrs
2017-09-27 14:56 | Kritika Vaid | Initial set up and install | Week#1 | 5h
2017-09-27 14:59 | Kritika Vaid | Create login page and sign up page for the UMLx. Login page requires username and password . Signup page requires username, password, email. The input information should be transferred into the backend. | Week#2 | 7h ( includes time to learn - understanding the code structure and watching video tutorials about node, express, and jade.)
2017-09-27 17:37 | Shashank Shekhar | Create functions to receive the uploaded data from the model upload page. #21 | Week#3 | 6h00m
2017-09-27 18:05 | Satya Ananya Pidikiti | Create activity diagrams according to the documents.[#24] | Week#3 | 6h 30m
2017-09-27 22:24 | Kritika Vaid | Create functions to store registration information and check login information. The data should be stored in MongoDB and queried from MongoDB. The database functions should be connected to the login and signup interfaces. | Week#3 | 10hr ( 5 hr watching videos on lynda about using node and mongo and 5 hr implementing the functionality )
2017-09-28 15:26 | Rachit Kulshrestha | Cocomo data collection | Week#3 | 5h
2017-09-28 15:27 | Rachit Kulshrestha | Histogram for project Type in R | Week#2 | 6h
2017-09-28 15:27 | Rachit Kulshrestha | Setup of machine and code | Week#1 | 4h
2017-10-04 13:51 | Sparshith Nairbalige Rai | #32 : Restructure the main page. | Week#4 | 9h
2017-10-04 14:35 | Kritika Vaid | #19 Initiate a repo for each registered enterprise user. add a type field to the user registration page, probably as a checkbox. If the user is registrated as a enterprise user, init a repo for the user. To create a new repo for a user, please refer to UMLxServices.js->app.get('/addRepo', function(req, res){}. The method for creating repo is there. Probably need to modify to plugin the user information to init a new repo for a specific user. Redirect to user login page if any other url is input and the user is not logged in. Probably there is some methods to do the automatically redirection for the nodejs/express plugin. | Week#4 | 10h
2017-10-09 22:20 | Shashank Shekhar | Implement the project data upload function. (#31) | Week#4 | 5h
2017-10-10 21:28 | Sparshith Nairbalige Rai | #38: Restructure the main page 2 | Week#5 | 12 | Finished 4 out of 3 tasks.
2017-10-11 10:17 | Satya Ananya Pidikiti | Data collection | Week#4 | 4.5
2017-10-11 10:17 | Satya Ananya Pidikiti | Class diagrams and sequence diagrams | Week#5 | 5h 25m
2017-10-11 22:14 | Shashank Shekhar | Create survey page for uploading UML model and use case evaluation #40 | Week#5 | 6h | Task 1 and 2 are complete along with the changes as per discussion
2017-10-13 04:54 | Rachit Kulshrestha | Scatter plot in R script | Week#4 | 4h | Learnt the scatter functionalities in R. how to plot it using R
2017-10-13 04:57 | Rachit Kulshrestha | Generate simulated projects | Week#5 | 10h | Learnt Node.Js. Analysed how to integrate logic with existing code base in github(eg: with UMLFileManager.js to extract data from CSV files) .Implemented logic using maps and kept on updating values as and when hierarchy was encountered
2017-10-18 16:05 | Sparshith Nairbalige Rai | #38: Task 4: reate the upload dialogs for the items in the "Load" menu: "Empirical data for models", "COCOMO Data". Just like what you did for "Empirical Data for Use Cases", #56: Restructure the repository analytics page. | Week#6 | 8hrs | Given issue is split across multiple tasks and tackle them individually. If work is very similar. First work on bringing up on UI then once approved then apply same to other. By doing so any changes need to UI could be identified in first shot and less work is need to change. Difficulties is not all images are available to replicate the design asked for and color codes where also need to be provided. It works in small project, when comes to big projects need to have one person who provides asset for the work.
2017-10-18 21:54 | Kritika Vaid | #57 Implementing user hierarchy- The registered normal user will be allocated with a "virtual space" in the enterprise user's repository, which means, even though there are other projects (created by other normal users) in the repository, at the first time, the newly registered user will be presented an empty list of projects in the main page, and the user can create his project, and the project created by the normal user will be shown up in enterprise account, but not shown up to other normal user account's main page. | Week#6 | 6h | For every normal user who is part of the enterprise (i.e created by the link sent by the enterprise admin) store the user id of admin ("enterpriseUserId" ) while registering this user and assign a new repo. When this normal user logs in, he/ she would be able to see only the projects in this repo as it happens now. Whereas when the admin for the enterprise logs in - instead of just getting projects belonging to repo of this user , get the projects in the repo of all the normal users that were created through this enterprise account.
2017-10-18 21:57 | Kritika Vaid | Implement User hierarchy [#39] | Week#5 | 7h | Fixed the bug mentioned. Also started implementing user hierarchy - now every time a new user signs up through a url like - http://localhost:8081/signup?uid=59d544ca940ffc2ed8fb9c8d where uid is the user id of enterprise user, this user is saved into the db with the enterpriseUserId = 59d544ca940ffc2ed8fb9c8d. However if you enter any non-existent uid in the url / or one which is not an enterprise user, the UI would pop up an error message.
2017-10-19 09:38 | Shashank Shekhar | created a separate survey page and save the data to MongoDB | Week#5 | 6h30m
2017-10-24 16:14 | Sparshith Nairbalige Rai | #66: High light the path and element within the use case diagram using D3.V4.min.js | Week#7 | 10hrs | In the beginning I thought we can't do this with img tag. That turned out to be right. When we are using svg better use object tag and provide data as svg image location. Which futher gives more feature to modify the image as we needed. It was really great experience as I didn't had any idea how to work with svgs. Thank you for this task.
2017-10-26 10:03 | Kan | Worked on the architecture for evaluators | Week#7 | 10h | Effort on 10/26
2017-10-26 10:26 | Kritika Vaid | Add the capability for enterprise users to send emails for add normal users #68 | Week#7 | 7h | added the capability to invite users by via email. I used the nodemailer package and created a Gmail account which is used to send out the mail with the invitation link. The link contains the email id and enterprise users id encrypted into json web token which is valid for 24 hrs.You can access this functionality on the UI by clicking on the 'envelope' icon near the login button on the top bar.
2017-10-26 10:54 | Shashank Shekhar | Upload n save error, reading related to d3v4 | Week#7 | 7h
2017-10-26 17:12 | Upendra Sandeep Muvva | Linear Regression Model | Week#7 | 11hrs | Creation from Paths Extracted from activity diagrams
2017-10-26 17:13 | Upendra Sandeep Muvva | Trending Charts for transactions | Week#6 | 8hrs
2017-10-26 17:14 | Upendra Sandeep Muvva | Synthesize the histograms into one histogram | Week#5 | 9hrs
2017-10-26 17:15 | Upendra Sandeep Muvva | Write path search algorithms for activity diagrams | Week#4 | 10hrs
2017-10-27 11:09 | Satya Ananya Pidikiti | Sequence diagrams | Week#7 | 5.5 hours
2017-10-27 12:41 | Rachit Kulshrestha | Building a neural net in R | Week#7 | 7h | Researched online how to implement neuralnet function in R
2017-10-27 12:42 | Rachit Kulshrestha | REsearch on neural net implemenation in R and research paper reading | Week#6 | 5h | Read the research paper and researched how to implement in R
2017-11-01 10:10 | Satya Ananya Pidikiti | Use case diagrams - data collection | Week#8 | 5h 30m
2017-11-02 12:15 | Shashank Shekhar | Integrate request activity monitor #48 | Week#8 | 6h00m
2017-11-02 12:44 | Kritika Vaid | Create profile pages for enterprise users and normal users. #87 | Week#8 | 6h
2017-11-08 17:12 | Sparshith Nairbalige Rai | #98: javascript object injection on the svg graphs generated from R. | Week#9 | 8hrs | injecting javascript into svg is possible. But requires a well structured svg. The one created by R isn't a well structured one.
2017-11-09 11:25 | Shashank Shekhar | Create a list page for all the submitted survey #100 | Week#8 | 6h00m | Also changes in upload page for post (removed params form URL), API to get data
2017-11-09 23:09 | Rachit Kulshrestha | Empirical study of factors on Neural Network | Week#9 | 6h | Ranking the factors acting in the neural network and analysis
2017-11-09 23:10 | Rachit Kulshrestha | Building Neural Network | Week#8 | 7h | Build neural network using the research paper
2017-11-14 14:43 | Kritika Vaid | Create the deregister function for the users. #109 | Week#9 | 5h | a user can be deactivated by hitting- /deactivateUser?uuid= any user can deactivate himself/herself an enterprise user can also deactivate users created via his account once the user is deactivated he is not able to log in. The enterprise user cannot see the projects of deactivated users. In case the user was logged in before he deactivated himself, he would not be forced logged out. However, when he tries to access any link, he will be taken to the login screen. Also if an enterprise user's account is deactivated, his invite link would also not work.
2017-11-15 09:43 | Satya Ananya Pidikiti | create test cases for main page | Week#9 | 10
2017-11-16 12:30 | Sparshith Nairbalige Rai | #112: Continue to explore on interactive R svg graphics | Week#10 | 8hrs | Did lot search on SVG generation using R. Since I had very less knowledge on R. I could vaguely understand explanation written. But one thing I understood is images generated using R is only for display purpose. They didn't design it to be structured one. So we might have to go with D3. I understand that D3 is not that easy to learn. Even I have very less knowledge on it. But What I found while searching is we have enough number of example online. Very good community help is always good for development. Since we have good support and easy implementation we can go with D3.
2017-11-16 15:32 | Shashank Shekhar | Create the detail page for the survey results (#100 & #108) | Week#9 | 7h00m
2017-11-22 12:06 | Satya Ananya Pidikiti | Further testing on account management page and use case panel. #122 | Week#10 | 5h
2017-11-22 16:17 | Sparshith Nairbalige Rai | #117: Develop data api for different types of operations and display the data in a pie chart | Week#11 | 8hrs | Initially chart rendering was done using R. I moved it to D3 for one of the chart. In this commit I moved it more better chart library highchart. Easy to use and understand
2017-11-24 14:24 | Shashank Shekhar | Create a folder to hold the upload survey data. #118 | Week#10 | 6h00m
2017-11-26 09:03 | Kritika Vaid | Investigate connecting Github account #119 | Week#10 | 6h
2017-11-29 20:57 | Sparshith Nairbalige Rai | #129 :Create histograms for the distributions using high charts | Week#12 | 10hrs | Used to highchart to generate graph. functions written can be used for other areas where similar chart is needed.
2017-11-29 23:35 | Upendra Sandeep Muvva | Stepwise Regression on Effort Data | Week#8 | 9hrs
2017-11-29 23:40 | Upendra Sandeep Muvva | stepwise regression of effort on a potential set of factors (#91) | Week#8 | 9h
2017-11-29 23:41 | Upendra Sandeep Muvva | Continue to Investigate the stepwise regression of effort on a potential set of factors (#103) | Week#9 | 9h
2017-11-29 23:42 | Upendra Sandeep Muvva | Compare cocomo estimation with use case point estimation (#105) | Week#10 | 13h
2017-11-29 23:42 | Upendra Sandeep Muvva | apriori estimation to the comparison (#123) | Week#11 | 10h
2017-11-29 23:43 | Upendra Sandeep Muvva | Create diagram to trace MMRE, PRED(.25), MSE over projects for the three effort estimator. (#133) | Week#12 | 9h