## Form Responses 1
Timestamp | Name | Task | Week | Effort | Description (Optional)
2017-09-23 20:51 | Upendra Sandeep | Environment set up and walk through | Week#1 | 3hr
2017-09-23 20:55 | Upendra Sandeep | Issue 10- Activity Diagram parsing | Week#2 | 8hrs
2017-09-24 19:18 | Vipin Dwivedi | Parsing XML output from Visual Paradigm. #12 | Week#2 | 4.5hrs
2017-09-24 19:19 | Vipin Dwivedi | Install Visual Paradigm, Get the app running | Week#1 | 3hrs
2017-09-26 13:39 | Sparshith Nairbalige Rai | #9 : Change the links at the bottom of the tab: RepoAnalytics/Analytics into buttons, #8: improve the projects list | Week#2 | 8hrs
2017-09-26 13:39 | Sparshith Nairbalige Rai | #22: create the file selection dialog to upload empirical data for use cases. | Week#3 | 10hrs
2017-09-27 14:56 | Kritika Vaid | Initial set up and install | Week#1 | 5h
2017-09-27 14:59 | Kritika Vaid | Create login page and sign up page for the UMLx. Login page requires username and password . Signup page requires username, password, email. The input information should be transferred into the backend. | Week#2 | 7h ( includes time to learn - understanding the code structure and watching video tutorials about node, express, and jade.)
2017-09-27 17:37 | Shashank Shekhar | Create functions to receive the uploaded data from the model upload page. #21 | Week#3 | 6h00m
2017-09-27 18:05 | Satya Ananya Pidikiti | Create activity diagrams according to the documents.[#24] | Week#3 | 6h 30m
2017-09-27 22:24 | Kritika Vaid | Create functions to store registration information and check login information. The data should be stored in MongoDB and queried from MongoDB. The database functions should be connected to the login and signup interfaces. | Week#3 | 10hr ( 5 hr watching videos on lynda about using node and mongo and 5 hr implementing the functionality )
2017-09-28 15:26 | Rachit Kulshrestha | Cocomo data collection | Week#3 | 5h
2017-09-28 15:27 | Rachit Kulshrestha | Histogram for project Type in R | Week#2 | 6h
2017-09-28 15:27 | Rachit Kulshrestha | Setup of machine and code | Week#1 | 4h
2017-10-04 13:51 | Sparshith Nairbalige Rai | #32 : Restructure the main page. | Week#4 | 9h
2017-10-04 14:35 | Kritika Vaid | #19 Initiate a repo for each registered enterprise user. add a type field to the user registration page, probably as a checkbox. If the user is registrated as a enterprise user, init a repo for the user. To create a new repo for a user, please refer to UMLxServices.js->app.get('/addRepo', function(req, res){}. The method for creating repo is there. Probably need to modify to plugin the user information to init a new repo for a specific user. Redirect to user login page if any other url is input and the user is not logged in. Probably there is some methods to do the automatically redirection for the nodejs/express plugin. | Week#4 | 10h
2017-10-09 22:20 | Shashank Shekhar | Implement the project data upload function. (#31) | Week#4 | 5h
2017-10-10 21:28 | Sparshith Nairbalige Rai | #38: Restructure the main page 2 | Week#5 | 12 | Finished 4 out of 3 tasks.
2017-10-11 10:17 | Satya Ananya Pidikiti | Data collection | Week#4 | 4.5
2017-10-11 10:17 | Satya Ananya Pidikiti | Class diagrams and sequence diagrams | Week#5 | 5h 25m
2017-10-11 22:14 | Shashank Shekhar | Create survey page for uploading UML model and use case evaluation #40 | Week#5 | 6h | Task 1 and 2 are complete along with the changes as per discussion
2017-10-13 04:54 | Rachit Kulshrestha | Scatter plot in R script | Week#4 | 4h | Learnt the scatter functionalities in R. how to plot it using R
2017-10-13 04:57 | Rachit Kulshrestha | Generate simulated projects | Week#5 | 10h | Learnt Node.Js. Analysed how to integrate logic with existing code base in github(eg: with UMLFileManager.js to extract data from CSV files) .Implemented logic using maps and kept on updating values as and when hierarchy was encountered
2017-10-18 16:05 | Sparshith Nairbalige Rai | #38: Task 4: reate the upload dialogs for the items in the "Load" menu: "Empirical data for models", "COCOMO Data". Just like what you did for "Empirical Data for Use Cases", #56: Restructure the repository analytics page. | Week#6 | 8hrs | Given issue is split across multiple tasks and tackle them individually. If work is very similar. First work on bringing up on UI then once approved then apply same to other. By doing so any changes need to UI could be identified in first shot and less work is need to change. Difficulties is not all images are available to replicate the design asked for and color codes where also need to be provided. It works in small project, when comes to big projects need to have one person who provides asset for the work.
2017-10-18 21:54 | Kritika Vaid | #57 Implementing user hierarchy- The registered normal user will be allocated with a "virtual space" in the enterprise user's repository, which means, even though there are other projects (created by other normal users) in the repository, at the first time, the newly registered user will be presented an empty list of projects in the main page, and the user can create his project, and the project created by the normal user will be shown up in enterprise account, but not shown up to other normal user account's main page. | Week#6 | 6h | For every normal user who is part of the enterprise (i.e created by the link sent by the enterprise admin) store the user id of admin ("enterpriseUserId" ) while registering this user and assign a new repo. When this normal user logs in, he/ she would be able to see only the projects in this repo as it happens now. Whereas when the admin for the enterprise logs in - instead of just getting projects belonging to repo of this user , get the projects in the repo of all the normal users that were created through this enterprise account.
2017-10-18 21:57 | Kritika Vaid | Implement User hierarchy [#39] | Week#5 | 7h | Fixed the bug mentioned. Also started implementing user hierarchy - now every time a new user signs up through a url like - http://localhost:8081/signup?uid=59d544ca940ffc2ed8fb9c8d where uid is the user id of enterprise user, this user is saved into the db with the enterpriseUserId = 59d544ca940ffc2ed8fb9c8d. However if you enter any non-existent uid in the url / or one which is not an enterprise user, the UI would pop up an error message.
2017-10-19 09:38 | Shashank Shekhar | created a separate survey page and save the data to MongoDB | Week#5 | 6h30m
2017-10-24 16:14 | Sparshith Nairbalige Rai | #66: High light the path and element within the use case diagram using D3.V4.min.js | Week#7 | 10hrs | In the beginning I thought we can't do this with img tag. That turned out to be right. When we are using svg better use object tag and provide data as svg image location. Which futher gives more feature to modify the image as we needed. It was really great experience as I didn't had any idea how to work with svgs. Thank you for this task.
2017-10-26 10:03 | Kan | Worked on the architecture for evaluators | Week#7 | 10h | Effort on 10/26
2017-10-26 10:26 | Kritika Vaid | Add the capability for enterprise users to send emails for add normal users #68 | Week#7 | 7h | added the capability to invite users by via email. I used the nodemailer package and created a Gmail account which is used to send out the mail with the invitation link. The link contains the email id and enterprise users id encrypted into json web token which is valid for 24 hrs.You can access this functionality on the UI by clicking on the 'envelope' icon near the login button on the top bar.
2017-10-26 10:54 | Shashank Shekhar | Upload n save error, reading related to d3v4 | Week#7 | 7h
2017-10-26 17:12 | Upendra Sandeep Muvva | Linear Regression Model | Week#7 | 11hrs | Creation from Paths Extracted from activity diagrams
2017-10-26 17:13 | Upendra Sandeep Muvva | Trending Charts for transactions | Week#6 | 8hrs
2017-10-26 17:14 | Upendra Sandeep Muvva | Synthesize the histograms into one histogram | Week#5 | 9hrs
2017-10-26 17:15 | Upendra Sandeep Muvva | Write path search algorithms for activity diagrams | Week#4 | 10hrs
2017-10-27 11:09 | Satya Ananya Pidikiti | Sequence diagrams | Week#7 | 5.5 hours
2017-10-27 12:41 | Rachit Kulshrestha | Building a neural net in R | Week#7 | 7h | Researched online how to implement neuralnet function in R
2017-10-27 12:42 | Rachit Kulshrestha | REsearch on neural net implemenation in R and research paper reading | Week#6 | 5h | Read the research paper and researched how to implement in R
2017-11-01 10:10 | Satya Ananya Pidikiti | Use case diagrams - data collection | Week#8 | 5h 30m
2017-11-02 12:15 | Shashank Shekhar | Integrate request activity monitor #48 | Week#8 | 6h00m
2017-11-02 12:44 | Kritika Vaid | Create profile pages for enterprise users and normal users. #87 | Week#8 | 6h
2017-11-08 17:12 | Sparshith Nairbalige Rai | #98: javascript object injection on the svg graphs generated from R. | Week#9 | 8hrs | injecting javascript into svg is possible. But requires a well structured svg. The one created by R isn't a well structured one.
2017-11-09 11:25 | Shashank Shekhar | Create a list page for all the submitted survey #100 | Week#8 | 6h00m | Also changes in upload page for post (removed params form URL), API to get data
2017-11-09 23:09 | Rachit Kulshrestha | Empirical study of factors on Neural Network | Week#9 | 6h | Ranking the factors acting in the neural network and analysis
2017-11-09 23:10 | Rachit Kulshrestha | Building Neural Network | Week#8 | 7h | Build neural network using the research paper
2017-11-14 14:43 | Kritika Vaid | Create the deregister function for the users. #109 | Week#9 | 5h | a user can be deactivated by hitting- /deactivateUser?uuid= any user can deactivate himself/herself an enterprise user can also deactivate users created via his account once the user is deactivated he is not able to log in. The enterprise user cannot see the projects of deactivated users. In case the user was logged in before he deactivated himself, he would not be forced logged out. However, when he tries to access any link, he will be taken to the login screen. Also if an enterprise user's account is deactivated, his invite link would also not work.
2017-11-15 09:43 | Satya Ananya Pidikiti | create test cases for main page | Week#9 | 10
2017-11-16 12:30 | Sparshith Nairbalige Rai | #112: Continue to explore on interactive R svg graphics | Week#10 | 8hrs | Did lot search on SVG generation using R. Since I had very less knowledge on R. I could vaguely understand explanation written. But one thing I understood is images generated using R is only for display purpose. They didn't design it to be structured one. So we might have to go with D3. I understand that D3 is not that easy to learn. Even I have very less knowledge on it. But What I found while searching is we have enough number of example online. Very good community help is always good for development. Since we have good support and easy implementation we can go with D3.
2017-11-16 15:32 | Shashank Shekhar | Create the detail page for the survey results (#100 & #108) | Week#9 | 7h00m
2017-11-22 12:06 | Satya Ananya Pidikiti | Further testing on account management page and use case panel. #122 | Week#10 | 5h
2017-11-22 16:17 | Sparshith Nairbalige Rai | #117: Develop data api for different types of operations and display the data in a pie chart | Week#11 | 8hrs | Initially chart rendering was done using R. I moved it to D3 for one of the chart. In this commit I moved it more better chart library highchart. Easy to use and understand
2017-11-24 14:24 | Shashank Shekhar | Create a folder to hold the upload survey data. #118 | Week#10 | 6h00m
2017-11-26 09:03 | Kritika Vaid | Investigate connecting Github account #119 | Week#10 | 6h
2017-11-29 20:57 | Sparshith Nairbalige Rai | #129 :Create histograms for the distributions using high charts | Week#12 | 10hrs | Used to highchart to generate graph. functions written can be used for other areas where similar chart is needed.
2017-11-29 23:35 | Upendra Sandeep Muvva | Stepwise Regression on Effort Data | Week#8 | 9hrs
2017-11-29 23:40 | Upendra Sandeep Muvva | stepwise regression of effort on a potential set of factors (#91) | Week#8 | 9h
2017-11-29 23:41 | Upendra Sandeep Muvva | Continue to Investigate the stepwise regression of effort on a potential set of factors (#103) | Week#9 | 9h
2017-11-29 23:42 | Upendra Sandeep Muvva | Compare cocomo estimation with use case point estimation (#105) | Week#10 | 13h
2017-11-29 23:42 | Upendra Sandeep Muvva | apriori estimation to the comparison (#123) | Week#11 | 10h
2017-11-29 23:43 | Upendra Sandeep Muvva | Create diagram to trace MMRE, PRED(.25), MSE over projects for the three effort estimator. (#133) | Week#12 | 9h