## Cocomo Effort Estimation
Team. NO. | Semester | PROJ | Effort (PM) | Effort (PH) | URL | Module | Size | EAF | NOM Effort DEV | EST Effort DEV | PROD | Staff | Effort(Optimistic) | Schedule(Optimistic) | PROD(Optimistic) | Staff(Optimistic) | Effort(Most Likely) | Schedule(Most Likely) | PROD(Most Likely) | Staff(Most Likely) | Effort(Perssimistic) | Schedule(Perssimistic) | PROD(Perssimistic) | Staff(Perssimistic)
1 | Fall 2015/Spring 2016 | f15a_PicshareApp_RA |  |  | ~\577 projects\fall15\projects\team01\team01b\FD | NA
2 | Fall 2015/Spring 2016 | f15b_PicShare | 8.95 | 1396.2 | ~\577 projects\fall15\projects\team02\team02b\new\FinalDeliverables | Picture Module | 2468 | 0.57 | 8.07 | 4.36 | 53 | 0.6 | 7.16 | 6.77 | 704.28 | 1.1 | 8.95 | 7.26 | 563.42 | 1.2 | 11.18 | 7.78 | 450.74 | 1.4
[6 empty] | Browse Module | 1943 | 0.58 | 6.36 | 3.66 | 53 | 0.5
[6 empty] | Profile Module | 630 | 0.33 | 2.06 | 0.67 | 93 | 0.1
3 | Fall 2015 | f15a_Lingggo | 12 | 1872 | ~\577 projects\fall15\projects\team03\team03a\FinalDeliverables | Match System | 1150 | 1.17 | 3.8 | 4.5 | 257.6 | 0.6 | 9.6 | 7.5 | 358.9 | 1.3 | 12 | 8.1 | 287.1 | 1.5 | 15 | 8.7 | 229.7 | 1.7
[6 empty] | Profile System | 1150 | 0.6 | 3.8 | 2.3 | 501.1 | 0.3
[6 empty] | Message System | 1150 | 1.37 | 3.8 | 5.3 | 218.8 | 0.6
4 | Fall 2015 | f15a_CombatConflict | 10.7 | 1669.2 | ~\577 projects\fall15\projects\team04\team04a\team04a\Artifacts\Development | InsertPHPPlugin | 126 | 0.88 | 0.5 | 0.4 | 290.3 | 0.1 | 8.6 | 7.2 | 249.3 | 1.2 | 10.7 | 7.7 | 199.4 | 1.4 | 13.4 | 8.2 | 159.6 | 1.6
[6 empty] | SQL Stats Plugin | 126 | 0.92 | 0.5 | 0.5 | 278.9 | 0.1
[6 empty] | Wordpress Site | 1890 | 1.33 | 7.4 | 9.9 | 191.8 | 1.3
5 | Fall 2015 | f15a_Tour_Conductor | 7.78 | 1213.68 | ~\577 projects\fall15\projects\team05\team05a\FD | Login and Profile | 920 | 0.41 | 3.19 | 1.32 | 698.34 | 0.2 | 6.22 | 6.55 | 903.93 | 0.9 | 7.78 | 7.03 | 723.14 | 1.1 | 9.72 | 7.55 | 578.52 | 1.3
[6 empty] | Tour Creation | 1540 | 0.38 | 5.34 | 2.01 | 767.34 | 0.3
[6 empty] | QueryModule | 315 | 0.21 | 1.09 | 0.23 | 1390.9 | 0
[6 empty] | Tour and Stop view Module | 2300 | 0.41 | 7.98 | 3.29 | 698.28 | 0.5
[6 empty] | Map and Navigation Module | 550 | 0.49 | 1.91 | 0.93 | 588.91 | 0.1
6 | Fall 2015 | f15a_ConstructionMeeting_MinutesApp | 2.9 | 452.4 | ~\577 projects\fall15\projects\team05\team05a\FD | Task FNS | 345 | 0.84 | 1 | 0.9 | 402 | 0.2 | 2.3 | 4.8 | 502.5 | 0.5 | 2.9 | 5.1 | 402 | 0.6 | 3.6 | 5.5 | 321.6 | 0.7
[6 empty] | Notification-I | 229 | 0.84 | 0.7 | 0.6 | 402 | 0.1
[6 empty] | Report Gen-I | 229 | 0.84 | 0.7 | 0.6 | 402 | 0.1
[6 empty] | Local Storage | 345 | 0.84 | 1 | 0.9 | 402 | 0.2
7 | Fall 2015 | f15a_NICE | 8.1 | 1263.6 | ~\577 projects\fall15\projects\team07\team07a\team07a\Development | E-commerce | 603 | 1.31 | 2 | 2.6 | 234.2 | 0.4 | 6.5 | 6.8 | 316 | 1 | 8.1 | 7.3 | 252.8 | 1.1 | 10.1 | 7.8 | 202.2 | 1.3
[6 empty] | multi-vendor | 804 | 1.31 | 2.6 | 3.4 | 234.2 | 0.5
[6 empty] | blog | 402 | 1 | 1.3 | 1.3 | 306 | 0.2
[6 empty] | vendors | 241 | 1 | 0.8 | 0.8 | 306 | 0.1

## Estimation Model Comparison
Team. NO. | Semester | PROJ | Actual Size (SLOC) | Estimated SLOC | Effort(Optimistic) | Effort(Most Likely) | Effort(Perssimistic) | Use Case Estimation | COCOMO Estimation | ACTUAL Effort
1 | fall2015/spring2016 | s16b_Picshare_RA | 8271 |  |  |  |  | 3113 | 3113 | 3113
2 | fall2015/spring2016 | s16b_Picshare_AA | 8561 | 5031 | 1088.32 | 1360.4 | 1699.36 | 1592 | 1592 | 1592
* Estimae SLOC: The sum of slocs for the modules. Please refer the "cocomo effort estimation" tab